## Draft EDAM Issue List 7152026
CAISO Public
ID | Title | Description | CC Impact | Status | Resolution | Impacted TD | Production Deployment Date | PRR | Impacted BAA | Comment
1 | CC 8076, 8086 - Incorrect Tier 1 Quantity Calculation for Intertie Resources (IRU/IRD) | ​​IRU imports calc using FMM max ex cap instead of pre-hour transmission profile for CISO, and IRD exports calc missing data for non-CISO EDAM BAA for pre-hour transmission profile.​ Caution: Resolution/System may not be accurate | 8076, 8086 | Pending Recal | Final resolution is pending on legal and policy’s guidance. Tentative solution is that both IRU imports and IRD exports will use pre-hour transmission profile for CISO and use FMM cleared energy schedule for non-CISO EDAM BAA. Also potentially, the IRU exports and IRD imports calc using FMM self-schedules will be replaced with FMM cleared energy schedules.​ | Retro to TD 5/1/2026 | 2026-07-08 | TBD - End of June Release | EDAM & ISO BAA | S​UG 6/17/26​​
2 | CC 64750 - UIE is not including the affected LAPs in Settlement Amount | CC 64750 not correctly calculating UIE for LAPs that have self scheduled load​​CC 64750 not correctly calculating UIE for LAPs that have self scheduled load | 64750 | Pending Recal | Updating drivers of amount calculations to align with how 6475 UIE calculates for CAISO to ensure all applicable LAPs are accounted for in amount calculations.​ | Retro to TD 5/1/2026 | 2026-07-08 | TBD - End of June Release | EDAM | S​UG 6/17/26​
3 | Wheel Export PC - Balanced ETC/TOR are getting access charges due to wrong wheel export quantity calculation. | Wheel export quantity calculation is incorrect for priority wheel through (PWT) and reservation (PWT resale), emphasized when there is contract schedules on the resource.​ | Wheel Export PC, 382, indirect to 384. | Pending Recal | Compute wheel export at resource level. Subtract balanced contract from gross export value and then compare with the difference of PWT and PWT resale. The larger value becomes the effective wheel export quantity subject to settlement. Also added PTB adjustment for wheel export qty.​ ​ | Retro to TD 11/1/2024, and actual impacted dates are TD 11/8-11/18/2024 for the T+21M. No other TDs were impacted so far due to no contract overlapping with PWT at a resource | 2026-07-08 | TBD - End of June Release | ISO BAA | S​UG 6/17/26​
6 | Dispute Issue: Missing shift factors impacting CRR Settlement | Missing shift factors for IRU and IRD resulted in incorrect Congestion Revenue calculations in Settlements. ​ Shift factors were not received from Market payload by the CRR application, leading to incomplete calculations in downstream.​​ ​ ​ ​ | 6700, 6790 | Open | Patch is in and deployed to testing. Validation is currently in progress. Impacted Trade Dates: 5/1/2026 - Ongoing. Once we get the fix in production, we will retrospectively correct from Trade Date 5/1/2026. We are hoping to make these corrections on T+70B the Settlement Statement.​ Note: this is laregly solved, one remaining issue that impacts CAISO, but not PGE or PAC. Went into Stage in 6/15​ | Trade Dates 5/1/2026 through 5/20/2026 will be corrected on T+70B Settlement Statement. This issue is resolved starting from Trade Date 5/21/2026​ |  |  | EDAM & ISO BAA | S​UG 6/17/26​
7 | Dispute Issue: Missing shift factors on the MPP Site. | Issue Description: Missing shift factors in the payload posted to the Market Participant Portal (MPP), impacting participants ability to perform validations. Root Cause: Shift factor data was missing in the payload, resulting in incomplete information being published to MPP.​ | 6700, 6790 | Open | Currently reposting missing shift factors. Coverage includes Trade Dates starting 5/1/2026 onward.​ Note: this is largely solved, one remaining issue that impacts CAISO, but not PGE or PAC. Went into Stage in 6/15​ | Trade Dates Starting 5/1/2026 |  |  | EDAM & ISO BAA | S​UG 6/17/26​
8 | Dispute Issue: Discrepancy in flows for IPPDCADLN_ITC and IPPUTAH_ITC impacting CRR Settlement. | Issue Description: Incorrect IFM (Integrated Forward Market) flow calculations are causing errors in Congestion Revenue calculations. Root cause: When interties are mapped to multiple ITCs (Intertie Constraints), the IFM flow calculation logic produces incorrect results, impacting downstream revenue allocations. | 6700, 6790 | Open | ​Patch is in and the team is performing testing. Once we get the fix in production, we will retrospectively correct from Trade Date 5/1/2026. We are hoping to make these corrections on T+70B Settlement Statement.​ ​Affects only CAISO CRR holders. Fix exists, but not in prod yet. | Trade Dates Starting 5/1/2026 |  |  | ISO BAA | 7/7 - Vendor fix in place and being tested; no estiamted date for production at this time. S​UG 6/17/26​
9 | Dispute Issue: Incorrect Claw-back calculation for IRU and IRD | Issue Description: Starting from Trade Date 5/1/2026, zero claw back values are being sent in the revenue adjustment payload to Settlements, leading to incorrect congestion revenue adjustments. Root cause: A gap in communication between Vendor and CAISO regarding requirement implementation (DAME BRS#7875) resulted in incorrect information in the payload.​ | 6700, 6790 | Open | ​Patch is in and the team is performing testing. Once we get the fix in production, we will retrospectively correct from Trade Date 5/1/2026. We are hoping to make these corrections on T+70B Settlement Statement.​ Change has been delivered. Check with Uma/Sriram. Only impacts CAISO CRR holders​ | Trade Dates Starting 5/1/2026 |  |  | ISO BAA | 7/7 - Vendor fix in place and being tested; no estiamted date for production at this time S​UG 6/17/26​
10 | Dispute Issue: Missing SCIDs in CRR Ownership Data | Issue Description: Missing SCIDs (30) in the Market Quality System (MQS) database are impacting CRR settlement calculations, leading to incomplete or incorrect revenue adjustments. impacts CRR Settlement calculations. Root cause: Required SCIDs were not populated in MQS, causing gaps in downstream settlements processing of charge codes.​ | 6700, 6790 | Open | Short-Term Workaround: CAISO is repopulating missing SCIDs starting from Trade Date 5/1/2026​ Permanent Fix: Working with Master File and Vendor to implement a systematic fix to prevent this issue​ | Trade Dates Starting 5/1/2026 |  |  | EDAM & ISO BAA | 7/7 - Manaul workaround in place. Retro active to 5/1; Should not impact settlement any more.​​ S​UG 6/17/26​
11 | IRD Issue related to MF | Impacted: Allocation CC8086 & CC8087 (indirect)​ | 8086, 8087 | Open | Went to production. Manual Fix for PCA Publishing Issues with RAOverlappingCapacityAllocationResult HPQC 93735, went to Stage on 6/17 and production on 6/18. Scernario dependent, may not have impacted PGE.​ | 6/2 & 6/4, 6/9, 6/11 |  |  | "PGE (for now) Settlements needs to confirm other customers impacted in Stage and Prod." | ​
12 | Market - Under certain conditions, RCU awards may violate UEL/UCL for off-line MSGs | Under investigation, these might turn out to be no defects at all but data issues or misunderstanding on our part on how the functionality is working ​ |  | Internal Review |  |  | 2026-07-08 |  |  | Fix in Production effective TD 7/8 onward​
13 | Market - Resources may not follow ramping limitations when awarding imbalance reserves | Under investigation, these might turn out to be no defects at all but data issues or misunderstanding on our part on how the functionality is working ​ |  | Internal Review
18 | Market - Shift factors reporting issues on SF file and CSV file | PROD: Shift factors for anode_id =0 in EMM_SCUC_INPUT_AGG_SF and in SF files.​ |  | Patch pending Validation | 6/22 - 2025_FALL_IFM_034.01.R9 MapTest ​ |  |  |  |  | 7/7 - YT - Fix in place effective TD 6/19 onward
23 | Overlapping RA data was not included in payload | CA Publishing Issues with RAOverlappingCapacityAllocationResult |  | Open | Went to production. Manual Fix for PCA Publishing Issues with RAOverlappingCapacityAllocationResult HPQC 93735, went to Stage on 6/17 and production on 6/18. Scernario dependent, may not have impacted PGE.​ |  |  |  | EDAM
24 | PROD: RUC award/commitment to MSG resources on the top of IFM is not passed to NA | Humboldt RUC Energy from MSG resources awarded in RUC not passed to NA. REN should be used in NA for RUC.​ |  | Open |  |  |  |  | EDAM
25 | SIBR - Performance during Bid Result retrieval - educational | CAISO reviewing retrieve performance based on timing and high peak Jrule processing to evaluate ​performance and reliability concerns with the RetrieveCurrentBidResults (SIBR) API, |  | Internal Review | [5 empty] | Moving forward, we recommend at least a 30-second wait between a submission and its corresponding retrieval, without multiple submissions occurring in this manner. Please let us know if any questions remain and we'd be happy to assist.​
26 | SIBR - Issue identified with rounding logic associated to DA awards received in SIBR which prevent correct self - schedule submissions to conform with the awards. |  |  | Internal Review | [5 empty] | ETA for fix 7/15/26
27 | SIBR - Issue identified in intertie mapping addressed through rule changes provided to vendor |  |  | Patch pending Validation | [5 empty] | 7/14 - patch scheduled for producton ~ 7/14
28 | SIBR - Transaction id were not recognized as an intertie award | Similar to CIDI 00301854​ |  | Closed
29 | Dispute Issue: Base ETSR Flag | ​During settlement processing, a timing-related processing issue resulted in the Base ETSR flag not being correctly picked up, despite the underlying records being terminated correctly. This created a timing gap between record termination and flag evaluation leading to incorrect inputs for Base ETSR Settlement calculations​. | 64600, 64700, 64770 | Pending Recal | Resettling the impacted Trade Dates will fix the issue because issue is timing-related.​ | Trade Dates 4/20/2026 and 4/21/2026 will be corrected on T+70B Settlement Statement. Trade Dates from 6/10/2025 through 6/12/2025 will be corrected on T+11M Settlement Statement. Trade Dates from 8/1/2024 through 8/7/2024 will be corrected on T+24M Settle |  |  | WEIM | S​UG 5/3/26
30 | Dispute Issue: Dynamic ETSR Settlement. | For Dynamic ETSRs, duplicate records have been observed for the following Bill Determinants (BD). This issue is caused by timing/sequencing of incoming payloads and is related with the Settlements code deployment for DAME/EDAM.BA_5M_RSRC_EIM_XFER_TO_BAA_TAG_QTY andBA_5M_RSRC_EIM_XFER_FROM_BAA_TAG_QTY​​ | 64770 | Pending Recal | Resettling the impacted Trade Dates will fix the issue because issue is timing-related. | Trade Dates 4/21/2026 - 4/29/2026 will be corrected on the T+70B Settlement Statement. |  |  | WEIM | S​UG 5/3/26
31 | Dispute Issue: Missing TSR Bill Determinant in Settlements | Settlements received ETSR and TSR input data, however, the associated records were subsequently terminated. This issue resulted in missing related BDs and led to incorrect ETSR and TSR settlement calculations. The impacted Trade Dates span from 5/1/2026 through 5/5/2026.​ | 8011, 8411, 8470, 8811, 64600, 64700 | Pending Recal |  | Trade Dates 5/1/2026 - 5/5/2026 will be corrected on T+70B Settlement Statement. Issue was resolved starting Trade Date 5/6/2026. |  |  | WEIM & EDAM | S​UG 5/3/26
33 | DA Congestion PC, RT Congestion PC | Transfer Congestion was being paid out but not collected.​ | 6790, 64770, 6774, 67740, 4989 | Pending Recal | Update Congestion Pre-Calcs and balancing for 4989 to correctly collect/ account for Transfer Congestion Amounts to then be allocated.​​ | TD 5/1 – 5/20 T-9B initial Statement. It will be automatically corrected on T-70B Statement • TD 5/21 onward T-9B initial Statement will be correct. | 2026-06-08 |  |  | ​SUG 6/10/26
34 | CC 8470 -Average Hourly FMM Price being used in Congestion calculation and incorrect sign | Incorrect Congestion Amounts calculated for FMM due to an averaging across the hour instead of by fifteen-minute granularity and reversed sign.​ | 8470 | Pending Recal | Remove -1 multiplier from RTD and FMM Congestion Amount calculations and replace FMM hourly average price with FMM fifteen-minute price in congestion amount calculations​ | TD 5/1 – 5/20 T-9B initial Statement. It will be automatically corrected on T-70B Statement • TD 5/21 onward T-9B initial Statement will be correct. | 2026-06-08 |  |  | ​SUG 6/10/26
35 | CC 8080 - RSE potential for negative price of average LAP price needs a floor of $0. | Incorrect Congestion Amounts calculated for FMM due to an averaging across the hour instead of by fifteen-minute granularity and reversed sign. | 8080 | Pending Recal | A Max function was added to the calculation of the Average LAP LMP to ensure that the minimum possible price would be $0 and not negative​​ | 5/1/2026-5/11/2026 (T9B), will be automatically fixed in T70B; T9B for TD on or after 5/12/2026 is good | 2026-05-22 |  | EDAM & ISO BAA | S​UG 6/3/26
36 | CC 6473 – Two Charge Types are missing in BD files | Reportability was set to “common” for two charge types, causing them not to appear in customer BD files.​​ Inability to shadow settlements all the way through 6473 due to the two charge types not present in the settlement files. No impact on Settlement amount.​​ | 6473 | Closed | The reportability was corrected to populate the charge types in the customer BD files.​ ​ | No financial impact to any TDs. • Reportability impact: 5/1/2026-5/11/2026 (T9B), will be automatically fixed in T70B; T9B for TD on or after 5/12/2026 is good. | 2026-05-22 |  |  | S​UG 6/3/26
37 | Wheel_Export_PC | Attributes were misaligned in formulation of BA_HRLY_RSRC_EXISTING_WHL_EXP@QUANTITY​ Output values of BA_HRLY_RSRC_EXISTING_WHL_EXP@QUANTITY were duplicated or triplicated. CC 382 and CC 384 amount will be impacted by this issue​. | 382, 384 | Pending Recal | Formulation of SPTO_SUB_WHL_EXP@QUANTITY was modified to include a summation of (N, z’) attributes​ | 4/20/2026-5/11/2026 (T9B), will be automatically fixed in T70B; T9B for TD on or after 5/12/2026 is good. • 1/29/2026-2/23/2026 (T70B), will be automatically fixed in T11M. T70B for TD on or after 2/24/2026 is good. | 2026-05-22 |  | ISO BAA | S​UG 6/3/26
38 | RT_Price_PC - Logical Interface meters creating incorrect UFE Settlement for MSS | Logical Interfaces for MSS were being incorrectly included in the UFE pricing calculations. Incorrect pricing for UFE for MSS. Impacted CC 6474, only impact CISO BAA (MSS). ​​ ​ | 6474 | Pending Recal | Filtering the Logical Interfaces to exclude them from the pricing calculations will ensure correct pricing calculations​ | 5/1/2026-5/11/2026 (T9B), will be automatically fixed in T70B; T9B for TD on or after 5/12/2026 is good. | 2026-05-22 |  | ISO BAA | S​UG 6/3/26
39 | CC 64600 - HASP Reversal incorrect calculation for EDAM | HASP Reversal for EDAM was calculating an incorrect value due to a frequency conversion issue​. Incorrect HASP Settlement would occur due to the incorrect value calculation. This impact non-CISO EDAM entities only.​​ | 64600 | Pending Recal | The formulas have been updated to correctly calculate HASP Reversal.​​ | 5/1/2026-5/11/2026 (T9B), will be automatically fixed in T70B; T9B for TD on or after 5/12/2026 is good. | 2026-05-22 |  | EDAM | S​UG 6/3/26
40 | CC 4989 - Incorrect rounding amount values in CC 4989 due to double counting of TSR congestion revenues. | Incorrect rounding amount values in CC 4989 due to double counting of TSR congestion revenues.​ | 4989 | Pending Recal | Remove the incorrect portion that goes to rounding CC 4989​. | 5/1/2026-5/11/2026 (T9B), will be automatically fixed in T70B; T9B for TD on or after 5/12/2026 is good. | 2026-05-22 |  |  | ​SUG 6/3/26
41 | CC384 and CC 374 - Invoicing Net Amount Issue | Incorrect invoice for CC 384 due to changed attribute set of current amount with SPTO implementation. The current amount from previous run (January 2026 initial) is missing when the January 2026 T+70B was calculating the net amount for invoicing purposes.​​ | 384, 374 | Open | Create an ad hoc PTB net amount adjustment to be able to reinstate the missing previous current amount value, to properly compute net amount and the invoice amount. This is expected to be used for Feb to April 2026 T+70B recalcs, and Oct 2025-Jan 2026 T+11M recalculations. This avoids the need for any supplemental invoice on the subject CCs. | Feb to April 2026 T+70B Settlement Statements. Oct 2025-Jan 2026 T+11M Settlement Statements. No financial impact to any monthly final invoice.​ | 2026-06-03 |  | ISO BAA | ​SUG 6/3/26
42 | FRP_PC and CC 7088 - FRP Neutrality issue involving GWA and duplicate cost allocation | There is duplicate cost allocation under the GWA BAA, a generation only BAA, when there is conflicting SC_ID (the EIM entity SC and any participating SC) which metered load is zero for certain intervals. Impact: Small amount of duplicated allocation under CC 7076, 7077, and 7087 was observed. Monthly FRP uncertainty cost allocation CCs 7078 and 7088 are expected to also have the issue until resolved​​​​ | 7076, 7077, 7087, 7078, 7088 | Pending Recal | Remove attribute BA_ID when checking for any generation only BAA. This is true only for second level allocation of unallocatable cost of forecasted movement to metered load or to the resource category buckets for uncertainty cost allocation. Updated FRP_PC and CC 7088​. ​ | 5/6/2026-5/21/2026 (T9B), will be automatically fixed in T70B; T9B for TD on or after 5/22/2026 should be good. | 2026-06-03 |  |  | ​SUG 6/3/26
43 | RT_NET_AMT_PC | FRP revenues (both forecasted movement and uncertainty award) included for RT BCR, which is incorrect.​​ Impact: Incorrect inclusion of FRP revenues for RT BCR. Impacted CC 6620 and 66200.​ | 6620, 66200 | Pending Recal | Fix FRP in eligibility flag to remove FRP revenues from RT BCR.​​​​​​ | 5/1/2026-5/21/2026 (T9B), will be automatically fixed in T70B; T9B for TD on or after 5/22/2026 should be good. | 2026-06-03 |  |  | ​SUG 6/3/26
44 | RT_Energy_PC - Duplicate BD, HASP Reversal | A driver issue was causing a duplication of records and settlements. Impact: Incorrect Settlement of HASP due to duplication. Impacted CC 6460 and CC 64600. | 6460, 64600 | Pending Recal | Corrected the equations to bring the inputs into alignment and included a HASP Reversal Flag into the equations.​ Note: Still some issues with HASP reversal payloads for PAC, sleaving this open to avoid confusion​​ | 5/1/2026-5/21/2026 (T9B), will be automatically fixed in T70B; T9B for TD on or after 5/22/2026 should be good. | 2026-06-03 |  | EDAM & ISO BAA | ​SUG 6/3/26
45 | RT_Energy_PC - Regulation Energy Calculation - Attribute Mismatch | Driver attributes were not in alignment, causing incorrect Regulation Energy Calculations. Impact: Incorrect Regulation Energy Quantity for EIM resources. Impacted CC 64700. | 64700 | Pending Recal | Update the calculations to align the drivers to correct the attribute mismatch.​ ​​​​fixed in stage after 6/1 | 5/1/2026-5/21/2026 (T9B), will be automatically fixed in T70B; T9B for TD on or after 5/22/2026 should be good. | 2026-06-03 |  | WEIM & EDAM | ​SUG 6/3/26
46 | RT_Energy_PC - Operational Adjustment (OA) Quantity Calculations for EDAM Intertie Resources | Day Ahead Schedules were not considered for OA Quantity Calculations on EDAM Intertie Resources. Impact: Incorrect Incremental Settlements for FMM IIE. Impacted CC 64700.​ | 64700 | Pending Recal | Update to include Day Ahead Schedules for EDAM Intertie Resources for correct incremental settlements for FMM IIE.​. | 5/1/2026-5/21/2026 (T9B), will be automatically fixed in T70B; T9B for TD on or after 5/22/2026 should be good. | 2026-06-03 |  | EDAM | ​SUG 6/3/26
47 | BA_DAY_RTD_BAA_GHG_REG_AREA_FLAG | This Bill Determinant had Logical Interties included in the mapping, which was assigning these resources unintentionally. Impact: Incorrectly including Logical Interties in GHG Offsets. CC 495 is impacted.​ | 495 | Pending Recal | Exclude the Logical Interties from appearing in this Bill Determinant to prevent these resources being associated to Real Time GHG Offset Settlement.​ | 5/1/2026-5/11/2026 (T9B), will be automatically fixed in T70B; T9B for TD on or after 5/12/2026 is good. | 2026-05-22 |  | EDAM & ISO BAA | ​SUG 6/3/26
48 | Dispute Issue: Incorrect DA Virtual Award Quantities. BA_HRLY_DA_VIR_AWARD_NODAL_QTY | Virtual Awards Movement was calculated and sent from upstream to map to this BD for TDs prior to 5/1/2026. Mapping of BA_HRLY_DA_VIR_AWARD_NODAL_QTY incorrectly incorporated the virtual awards movement amount sent from upstream. Impacted CC 6013, 6073, 6985, 4560; indirectly CCs 6774, 67740, 6636, 6477 & 6478.​​ | Directly impacted: 6013, 6073, 6985, 4560. Indirectly impacted: 6774, 67740, 6636, 6477 and 6478. | Pending Recal | Stop the virtual awards movement calculation for TDs prior to 5/1/2026​. | Trade Dates 2/7/2026-3/6/2026 will be corrected fixed on the T+11M Settlement Statement Any T+70B TD on or after 3/7/2026 has no issues. Trade Dates 4/25/2026-4/30/2026 will be corrected on the T+70B Settlement Statement. Any T+9B TD on or after 5/1/2 |  |  | ISO BAA | ​SUG 6/3/26
50 | Dispute Issue: IRUC/RCUC Capacity Calculation issues under the following conditions – When the resource is offline in IFM. | When the resource is offline in IFM (i.e., no Energy Awards) but still has IR (Imbalance Reserve) and RC (Residual commitment), the current logic does not calculate RCUC correctly. This issue resulted in incorrect RCU Settlements. The issue has been reviewed with Policy, and based on their guidance, the calculation logic will be updated for both IRUC and RCUC. No impact on IRD and RCD capacity calculations. ​​ | 8071, 8800 | Open | Fix is WIP. Once we get the fix, will apply corrections retrospectively from Trade Date 5/1/2026. We will provide an update regarding the fix in future SUG meeting.​​ for 7/1 TD, implemented fixes.​ | Trade Dates Starting 5/1/2026 |  |  | EDAM & ISO BAA | ​SUG 6/3/26
51 | Dispute Issue: Incorrect IRU Tier 1 Allocation Quantities for Import Resources. | For Import and Export resources, operational PMIN and PMAX values are not defined. As a result, the Market Quality System (MQS) does not calculate the FMM Max Ex Cap quantity for import resources. Settlements currently does not incorporate pre-hour transmission schedule tags when deriving the IRU Tier 1 allocation quantity. This gap has resulted in inaccurate IRU Tier 1 allocation settlement calculations. We use the same pre-hour transmission schedule tags for IRD Tier 1 allocation for Export resources as well. The export side calculations have been implemented correctly. | 8076 | Open | The fix will be included in next Settlements release (Not included in June 3rd release). Once the fix is available, we will make corrections retrospectively from Trade Date 5/1/2026.​ Going in 7/8 release. For TD 6/28 init onwards​ | Trade Dates Starting 5/1/2026 | 2026-07-08 |  | EDAM & ISO BAA | ​SUG 6/3/26
52 | Dispute Issue: Missing Data in Expected Energy Allocation report in CMRI. | An issue was identified with missing data in the Expected Energy Allocation (EEA) Details report within CMRI. Although the data was present in the underlying database, it was not being published to the report as expected. IT implemented an urgent patch to address the publishing issue, and the missing data has since been successfully populated in the EEA Details report. There were no discrepancies observed in the Expected Energy (EE) report within CMRI or in Settlements calculations. The issue was observed only for Trade Date 5/3/2026. ​ | None | Closed | Patch to address the publishing issue, and the missing data has since been successfully populated in the EEA Details report. | 5/3/2026 |  |  | ISO BAA | ​SUG 6/3/26
53 | Dispute Issue: Incorrect CRR information in CMRI impacting Settlement Validation. | ​An issue was identified involving incorrect Congestion Revenue Rights (CRR) information in CMRI. This discrepancy impacted SC’s ability to accurately validate CRR hourly settlement results. This issue has since been resolved, and the corrected data has been successfully updated in CMRI. Market participants may now access and download the revised reports for the impacted trade dates. | 6700 | Closed | CMRI has been updated with correct data.​ | 5/1/2026 - 5/13/2026 |  |  | ISO BAA | ​SUG 6/3/26
58 | Incorrect Virtual Award Quantity | The CMRI reflected the correct Virtual Award Quantity; however, this quantity was inaccurately represented in Settlements due to an incorrect mapping. ​ ​ | 6013 and the respective allocation charge codes. | Pending Recal | The mapping issue has now been identified and resolved. Corresponding corrections will be incorporated and reflected in the T+70B Settlement Statement​ ​ | 4/25/2026 through 4/30/2026 (T+9B) | 2026-05-20 |  |  | S​UG 5/20/26
59 | Missing APN_TYPE (Attr14) | Incorrect mapping issue in Settlements created incorrect calculations for a few of the charge codes. | 495, 6011, 6477, 6774, 6788, 8011, 8404, 8704, 64770 and 67740 and the respective allocation charge codes. | Pending Recal | The mapping issue has now been identified and resolved. Corrections will be incorporated and reflected in the T+70B Settlement Statement.​​ | 5/1/2026 through 5/3/2026 |  |  |  | S​UG 5/20/26​
61 | Missing FMM Awards for TD 5/8/2026, HE06, Interval 1 | We have identified missing FMM awards for HE06, Interval 1. This issue is related to market disruption.​ | 6460, 64600, 6470, 64700 and the respective allocation charge codes. | Pending Recal | Corrections will be applied and reflected in the T+70B Settlement Statement​ Timing issue | 5/8/2026 |  |  |  | S​UG 5/20/26
62 | Missing FMM Awards for TD 5/9/2026, HE24 | We have identified missing FMM awards for HE24. This issue is related to market disruption.​ | 6460, 64600, 6470, 64700 and the respective allocation charge codes. | Pending Recal | Corrections will be applied and reflected in the T+70B Settlement Statement​. | 5/9/2026 |  |  |  | S​UG 5/20/26
63 | No data in EDAM Balanced Contract Resources table in CMRI | This report is under External Entities > Extended Day-Ahead Market > EDAM Balanced Contract Resources​.​​​ | None | Open | CAISO will populate the relevant data soon. Based on our observations, no impact on Settlements Charge Code​​​s. | Starting from 5/1/2026 |  |  | EDAM | S​UG 5/20/26
64 | Missing settlement for CC 4566 and 4567 for TD 4/20-4/23 published initial | GMC for system operations under the split CC 4566 and 4567 is zero. The input data for BA_DAY_EDAM_ENTITY_FLAG for CISO BAA was replaced incorrectly with effective date TD 5/1/2026​​. Additional background: A documentation only change, an implementation note under CC 4567 for below formula, shall be provided in the BPM update to CC 4567 (Emergency PRR).​​ | 4566, 4567 | Pending Recal | This will be resolved in the next run cycle at T+70B​. | 4/20/2026 - 4/23/2026 |  |  |  | ​SUG 5/6/26
65 | No contracts balancing for TD 4/20-4/23/2026 initial | For these TDs, there will be no congestion hedge; no valid and balanced contract quantity exemptions to demand resource’s metered/measured demand allocations such as in CC 6790, 6774, 6477, 6636, 6678, Wheel export, and HVAC. Also, resources with TOR contract types will be subject to CC 4560 and 4566/4567 instead of 4563.​​​​ | CC 6790, 6774, 6477, 6636, 6678 Resources with TOR contract types will be subject to CC 4560 and 4566/4567 instead of 4563 | Pending Recal | This will be resolved in the next run cycle at T+70B.​ | 4/20/2026 - 4/23/2026 |  |  |  | ​SUG 5/6/26
67 | EDAM High: EIM Schedules by Priority Type | 6/15 Andrea: I still do not see any TSR Type 1 resources in the EIM Schedules by Priority Type CMRI report. I used trade date 6/9/2026 in stage for my test. I can see in SIBR we have a number of Type 1 Resources that do not show up in this report for this trade date in Stage. 6/16 Trang: have a fix for TSR in RT report that needs to be applied to our internal environment and validated there, and then will be promoted to Stage. ​ |  | Open | CMRI report issue of market data | 6/9 |  |  | PGE | Patch applied to production on 07/06/2026. The TSRs are now showing up in this report. ​
68 | EDAM Medium: CC8076 missing intervals BA15MResFMMMaxExCap | 6/11 Andrea: PGE is waiting for adequate Stage settlement statement to validate this logic. Per our meeting with Uma Manoj Bryan and YesEnergy staff on 6/4/2026. Market Simulation Statements for PGE published in late April 2026 and May 2026 were incomplete. SIBR Bids rolled over from Day Ahead to Real Time were incomplete and MSQ data into settlements were incomplete.​ | 8076 | Pending Customer Validation | Not a defect; need to educate PGE on design |  |  |  | EDAM
69 | EDAM High: Missing results in EDAM Balanced Contract Resource CMRI report and Settlement of CC8704 DA Cong Offset | Question: In CMRI EDAM Balanced Contract Resources, What is the difference between “Market” Day Ahead, Post Day Ahead and Final? I looked in the BPM for Market Instruments and did not find a section for this report. Ref: CIDI 00299504 I think the behavior in CIDI ticket 00299504 is impacting Balanced Contract Resource CMRI and our settlement of CC8704 billing determinant BA_HRLY_RSRC_DA_BALANCE_CONTRACT_SCHD@QUANTITY and BA_HRLY_RSRC_OATT_CONTRACT_CONG_CREDIT@AMOUNT. ​ | 8704, 6011 | Open | CMRI report issue (Settlement can handle) |  |  |  | PGE
70 | EDAM Med: ETC BA Hourly Load Balanced Contract Quantity missing | CC8077 and CC8076 use BASettlementIntervalResourceFinalBalancedContractCRNFilteredQuantity CC8077, CC8807, CC8087, CC8817 BAHourlyTotalLoadBalancedContractQuantity Calculated in PC ETC TOR CVR. This value will be negative for LOAD and ETIE resource types According to the Balanced Contract Report PGEM Load resource ELAP_PGE_PGEM_LOAD has 144 MWs of ETC Balanced Contract quantity on 6/11/2026 using CRN PGE_PGEE_ETC_BPAP and PGE_PGEE_ETC_PAC. PGEN has never received this determinant in their MRIS statement file. ​ | 8077, 8076 | Open |  |  |  |  | PGE | 7/6: We have validated RT CRN balancing for the requested Charge codes for TD 6/30/2026 STAGE, and the calculations are accurate. In addition, the initial had correct values for 6/23, the recalc made it worse, don't rely on the RECALK. In particular, the two bill_determinants are matching in nonzero values BA_5M_RSRC_FINAL_BALANCE_CONTRACT_CRN_FILTERED@QUANTITY BA_HRLY_TOT_LOAD_BALANCED_CONTRACT@QUANTITY on an hourly basis, if we filter only on LOAD resource types and do hourly aggregations.​
71 | EDAM Med: CC8011 Missing Transient TSR | The zero MW Energy Award was not making it to the data base, yet the resource had IR Award. Without this 0MW seen in the Award table the RTM Bid was not generated so no downstream bid for Post Market or Settlement. The IR should have been there for Settlement. ​ ​--- On Trade Date 6/11/2026 Recalc, SC PGEN, CC 8011 Day Ahead Imbalance Reserve Transfer Revenue Settlement I am having trouble validating the BABAATransferLocationNetIRQuantity and BAATransferLocationNetIRQuantity. It looks like the MWs related to PGEN_PGE_CISO_MALIN500_I_2_JD are in my CC8011 settlement result but the below 22 Transient Type 2 TSRs do not show up. All awards are at the same intertie of Malin500. PGEN-PGE_CISO_MALIN500_I-2-CISO-1 PGEN-PGE_CISO_MALIN500_I-2-CISO-10 PGEN-PGE_CISO_MALIN500_I-2-CISO-11 … ​ | 8011 | Patch pending Validation | When TSR have DA awards , RT bids are not created​ |  |  |  | PGE | Vendor provided manual fix in testing. Target prod by 7/14 on SIBR patch 32
72 | Flex Ramp interval replacement price correction in WSU | For RTM 6/23, MVQA requested price corrections for interval replacement for both FRP and Energy + FRP. We noticed that FRP is no longer available as an interval replacement option in the PCA UI. Please advise on how to proceed. Would selecting the "ALL" commodity type be appropriate for the Energy + FRP correction? How should we handle the correction for the FRP commodity type, given that it is no longer available as an option? FRP interval replacement is an important requirement. The Price Correction tool previously supported this functionality. ​ |  | Patch pending Validation | Per Monique - The “All" button includes both energy and FRP. Please use that for the situation below.​If you are only processing FRP, we can do a back-end workaround to get these through while the defect gets assessed. |  |  |  |  | 7/7 - Manual workaround available
73 | Market - Clawback T+1 and T+8 runs for TD 6/18/2026 failed on LOAD_SF Processing Step | Clawback T+1 and T+8 runs failed on TD 6/18/2026 on LOAD_SF processing step. Please look into the root cause as this issue has resulted in no clean Clawback runs for this TD. This will possibly cause delays in invoicing or publishing of erroneous CRR settlement results.​ |  | Open
74 | Dispute Issue: Missing Capacity Calculation for MSG Resources. | RTPD capacity for MSG (Multi-Stage Generator) resources was calculated correctly, but due to a processing issue, all corresponding RTPD capacity records were deleted. Missing records resulted in missing capacity inputs, which subsequently caused incorrect IR (Imbalance Reserve) and RC(Residual Commitment) settlement calculations.​​ | 8071, 8081, 8800, 8810 and the respective allocation charge codes. | Pending Recal | Data is source system has been restored for impacted MSG resources and Trade Dates. ​ | Trade Dates 5/1/2026 - 5/20/2026 will be corrected on the T+70B Settlement Statement. Issue was resolved starting Trade Date 5/21/2026 |  |  | EDAM & ISO BAA | SUG 6/3/26
75 | CC 384 Non-subscriber generation quantity not calculating for SPTO, and null BA_ID attribute created incorrectly for CC 384 and 374 | CC 384 Non-subscriber generation quantity not calculating for SPTO, and null BA_ID attribute incorrectly created for CC 384 and 374 settlement due to SPTO intertie allocation amount​ | Wheel Export PC, 382, and 384. Indirect impact to 374 | Open | Update mapping for generation subscriber quantity to link resource to the SPTO, update existing and create new formulas to fix SPTO generation and intertie allocation amount.​ | Retro to TD 10/1/2025 |  |  | ISO BAA | SUG 7/8/26 Note: This issue was not a result of EDAM but will be fixed as part of the 7/8/2026 release.
76 | PROD: Duplicate records in SF and SF CSV files. |  |  | Closed | [5 empty] | 7/7 = YT - Fix in Production for TD 7/8 onward
77 | FMM ex-post capacities are not created for online resourcesM | MQS issue (affecting Colstrip resource) where FMM ex-post capacities are not created for online resources when IR/RC flags in MF are set to 'N'. Should be created regardless. This ultimately affects IRU Tier 1 allocation.CC 8076, 8086Discussing with Siemens 7/13. Communicated at noon on 7/13 to PGE/Andrea​ | 8076, 8086 | Open |  |  |  |  | EDAM
78 | Incorrect calculation of FMM LEL and FMM UEL | Defect 94059 (dup. of 94054)Incorrect calculation of FMM LEL and FMM UEL when the resource submits self-schedule with no economic bidsCC 8076, 8086​Discussing with Siemens7/13. Communicated at noon on 7/13 to Andrea |  | Open
79 | Load UIE not working | Defect 94074Fix in place last week for load UIE not working.​PGE aware, PAC filed dispute also. |  | Open