## EDAM Issues List
CAISO PUBLIC
ID | Title | Description | Impacted BAA | CC Impact | BD | PRR | Status | Production Deployment Date | Impacted TD | Impacted Scope | Resolution | Comment
1 | CC 8076, 8086 - Incorrect Tier 1 Quantity Calculation for Intertie Resources (IRU/IRD) | ​​IRU imports calc using FMM max ex cap instead of pre-hour transmission profile for CISO, and IRD exports calc missing data for non-CISO EDAM BAA for pre-hour transmission profile.​ Caution: Resolution/System may not be accurate | EDAM & ISO BAA | 8076, 8086 | BA_HRLY_IMPORT_RSRC_IRU_TIER1_ALLOC@QUANTITY,BA_HRLY_EXPORT_RES_IRD_TIER1_ALLOC@QUANTITY | 1687 | Pending Recal | 7/9/2026 | Retro to TD 5/1/2026 | ​Impacts PGE in Stage​ | Final resolution is pending on legal and policy’s guidance. Tentative solution is that both IRU imports and IRD exports will use pre-hour transmission profile for CISO and use FMM cleared energy schedule for non-CISO EDAM BAA. Also potentially, the IRU exports and IRD imports calc using FMM self-schedules will be replaced with FMM cleared energy schedules.​ | S​UG 6/17/26​​
2 | CC 64750 - UIE is not including the affected LAPs in Settlement Amount | CC 64750 not correctly calculating UIE for LAPs that have self scheduled load​​CC 64750 not correctly calculating UIE for LAPs that have self scheduled load | EDAM | 64750 | BA_5M_RSRC_EIM_UIE_LAP_AMT@AMOUNT | 1687 | Pending Recal | 7/9/2026 | Retro to TD 5/1/2026 | ​Impacts PGE in Stage​ | Updating drivers of amount calculations to align with how 6475 UIE calculates for CAISO to ensure all applicable LAPs are accounted for in amount calculations.​ | S​UG 6/17/26​
3 | Wheel Export PC - Balanced ETC/TOR are getting access charges due to wrong wheel export quantity calculation. | Wheel export quantity calculation is incorrect for priority wheel through (PWT) and reservation (PWT resale), emphasized when there is contract schedules on the resource.​ | ISO BAA | Wheel Export PC, 382, indirect to 384. | BA_HRLY_INTERTIE_WHL_EXP@QUANTITY | 1687 | Pending Recal | 7/9/2026 | Retro to TD 11/1/2024, and actual impacted dates are TD 11/8-11/18/2024 for the T+21M. No other TDs were impacted so far due to no contract overlapping with PWT at a resource |  | Compute wheel export at resource level. Subtract balanced contract from gross export value and then compare with the difference of PWT and PWT resale. The larger value becomes the effective wheel export quantity subject to settlement. Also added PTB adjustment for wheel export qty.​ ​ | S​UG 6/17/26​
6 | Dispute Issue: Missing shift factors impacting CRR Settlement | Missing shift factors for IRU and IRD resulted in incorrect Congestion Revenue calculations in Settlements. ​ Shift factors were not received from Market payload by the CRR application, leading to incomplete calculations in downstream.​​ ​ ​ ​ | EDAM & ISO BAA | 6700, 6790 | BA_DAY_CRR_NOTIONAL_AMT, BA_DAY_CRR_OFFSET_AMT |  | Pending Recal |  | Trade Dates 5/1/2026 through 5/20/2026 will be corrected on T+70B Settlement Statement. This issue is resolved starting from Trade Date 5/21/2026​ | ​CRR Holders | Patch is in and deployed to testing. Validation is currently in progress. Impacted Trade Dates: 5/1/2026 - Ongoing. Once we get the fix in production, we will retrospectively correct from Trade Date 5/1/2026. We are hoping to make these corrections on T+70B the Settlement Statement.​ Note: this is laregly solved, one remaining issue that impacts CAISO, but not PGE or PAC. Went into Stage in 6/15​ | S​UG 6/17/26​
7 | Dispute Issue: Missing shift factors on the MPP Site. | Issue Description: Missing shift factors in the payload posted to the Market Participant Portal (MPP), impacting participants ability to perform validations. Root Cause: Shift factor data was missing in the payload, resulting in incomplete information being published to MPP.​ | EDAM & ISO BAA | 6700, 6790 | BA_DAY_CRR_NOTIONAL_AMT, BA_DAY_CRR_OFFSET_AMT |  | Pending Recal |  | Trade Dates Starting 5/1/2026 | All SCs using shift factors for validation. ​ ​ | Currently reposting missing shift factors. Coverage includes Trade Dates starting 5/1/2026 onward.​ Note: this is largely solved, one remaining issue that impacts CAISO, but not PGE or PAC. Went into Stage in 6/15​ | S​UG 6/17/26​
8 | Dispute Issue: Discrepancy in flows for IPPDCADLN_ITC and IPPUTAH_ITC impacting CRR Settlement. | Issue Description: Incorrect IFM (Integrated Forward Market) flow calculations are causing errors in Congestion Revenue calculations. Root cause: When interties are mapped to multiple ITCs (Intertie Constraints), the IFM flow calculation logic produces incorrect results, impacting downstream revenue allocations. | ISO BAA | 6700, 6790 | BA_DAY_CRR_NOTIONAL_AMT, BA_DAY_CRR_OFFSET_AMT |  | Open |  | Trade Dates Starting 5/1/2026 | CRR holders​ | ​Patch is in and the team is performing testing. Once we get the fix in production, we will retrospectively correct from Trade Date 5/1/2026. We are hoping to make these corrections on T+70B Settlement Statement.​ ​Affects only CAISO CRR holders. Fix exists, but not in prod yet. | 7/7 - Vendor fix in place and being tested; no estiamted date for production at this time. S​UG 6/17/26​
9 | Dispute Issue: Incorrect Claw-back calculation for IRU and IRD | Issue Description: Starting from Trade Date 5/1/2026, zero claw back values are being sent in the revenue adjustment payload to Settlements, leading to incorrect congestion revenue adjustments. Root cause: A gap in communication between Vendor and CAISO regarding requirement implementation (DAME BRS#7875) resulted in incorrect information in the payload.​ | ISO BAA | 6700, 6790 | BA_DAY_CRR_CLAWBACK_AMT |  | Closed | 7/17/2026 | Trade Dates Starting 5/1/2026 | CRR holders | ​Patch is in and the team is performing testing. Once we get the fix in production, we will retrospectively correct from Trade Date 5/1/2026. We are hoping to make these corrections on T+70B Settlement Statement.​ Change has been delivered. Check with Uma/Sriram. Only impacts CAISO CRR holders​ | 7/7 - Vendor fix in place and being tested; no estiamted date for production at this time S​UG 6/17/26​
10 | Dispute Issue: Missing SCIDs in CRR Ownership Data | Issue Description: Missing SCIDs (30) in the Market Quality System (MQS) database are impacting CRR settlement calculations, leading to incomplete or incorrect revenue adjustments. impacts CRR Settlement calculations. Root cause: Required SCIDs were not populated in MQS, causing gaps in downstream settlements processing of charge codes.​ | EDAM & ISO BAA | 6700, 6790 | BA_DAY_CRR_CLAWBACK_AMT |  | Closed | 6/17/2026 | Trade Dates Starting 5/1/2026 | CRR holders ​ | Short-Term Workaround: CAISO is repopulating missing SCIDs starting from Trade Date 5/1/2026​ Permanent Fix: Working with Master File and Vendor to implement a systematic fix to prevent this issue​ | 7/7 Manul workaround in place. Should not impact settlement any more. Fix is in production as of 6/17 date; updated retroactive from 5/1/26 onwards​ S​UG 6/17/26​
11 | IRD Issue related to MF | Impacted: Allocation CC8086 & CC8087 (indirect)​ | "PGE (for now) Settlements needs to confirm other customers impacted in Stage and Prod." | 8086, 8087 | N/A |  | Open |  | 6/2 & 6/4, 6/9, 6/11 |  | Went to production. Manual Fix for PCA Publishing Issues with RAOverlappingCapacityAllocationResult HPQC 93735, went to Stage on 6/17 and production on 6/18. Scernario dependent, may not have impacted PGE.​ ​ | ​
12 | Market - Under certain conditions, RCU awards may violate UEL/UCL for off-line MSGs | Under investigation, these might turn out to be no defects at all but data issues or misunderstanding on our part on how the functionality is working ​ |  |  | BA_HRLY_RSRC_RCU_AWARD_QTY,BA_HRLY_RSRC_RCD_AWARD_QTY | 1687 | Internal Review | 7/9/2026 |  |  |  | Fix in Production effective TD 7/8 onward​
13 | Market - Resources may not follow ramping limitations when awarding imbalance reserves | Under investigation, these might turn out to be no defects at all but data issues or misunderstanding on our part on how the functionality is working ​ |  |  | N/A |  | Internal Review
18 | Market - Shift factors reporting issues on SF file and CSV file | PROD: Shift factors for anode_id =0 in EMM_SCUC_INPUT_AGG_SF and in SF files.​ |  |  | N/A |  | Patch pending Validation |  |  |  | 6/22 - 2025_FALL_IFM_034.01.R9 MapTest ​ | 7/7 - YT - Fix in place effective TD 6/19 onward
23 | Overlapping RA data was not included in payload | CA Publishing Issues with RAOverlappingCapacityAllocationResult | EDAM |  | BA_15M_RSRC_IRU_RA_OVERLAP_CAP_QTY,BA_15M_RSRC_RCU_RA_OVERLAP_CAP_QTY,BA_15M_RSRC_IRD_RA_OVERLAP_CAP_QTY,BA_15M_RSRC_RCD_RA_OVERLAP_CAP_QTY |  | Open |  |  |  | Went to production. Manual Fix for PCA Publishing Issues with RAOverlappingCapacityAllocationResult HPQC 93735, went to Stage on 6/17 and production on 6/18. Scernario dependent, may not have impacted PGE.​ | Impact: Data not showing in OASIS report​
24 | PROD: RUC award/commitment to MSG resources on the top of IFM is not passed to NA | Humboldt RUC Energy from MSG resources awarded in RUC not passed to NA. REN should be used in NA for RUC.​ | EDAM |  | N/A |  | Open |  |  | No direct external impact. Internal only​
25 | SIBR - Performance during Bid Result retrieval - educational | CAISO reviewing retrieve performance based on timing and high peak Jrule processing to evaluate ​performance and reliability concerns with the RetrieveCurrentBidResults (SIBR) API, |  |  | N/A |  | Closed |  |  |  |  | Moving forward, we recommend at least a 30-second wait between a submission and its corresponding retrieval, without multiple submissions occurring in this manner. Please let us know if any questions remain and we'd be happy to assist.​
26 | SIBR - Issue identified with rounding logic associated to DA awards received in SIBR which prevent correct self - schedule submissions to conform with the awards. | Modify SIBR rules 31441, 31445, 31448 part of the 12.3.5.1 rule set.​ ​ |  |  | N/A |  | Internal Review |  |  |  |  | ETA for fix 7/15/26
27 | SIBR - Issue identified in intertie mapping addressed through rule changes provided to vendor |  |  |  | N/A |  | Patch pending Validation |  |  |  |  | 7/14 - patch scheduled for producton ~ 7/14
28 | SIBR - Transaction id were not recognized as an intertie award | Similar to CIDI 00301854​ |  |  | N/A |  | Closed
29 | Dispute Issue: Base ETSR Flag | ​During settlement processing, a timing-related processing issue resulted in the Base ETSR flag not being correctly picked up, despite the underlying records being terminated correctly. This created a timing gap between record termination and flag evaluation leading to incorrect inputs for Base ETSR Settlement calculations​. | WEIM | 64600, 64700, 64770 | BA_DAY_RSRC_BASE_ETSR_FLAG,RSRC_ETSR_ELECT_STLMT_FLAG | N/A | Pending Recal | N/A - It should get corrected in the next settlement cycle. | Trade Dates 4/20/2026 and 4/21/2026 will be corrected on T+70B Settlement Statement. Trade Dates from 6/10/2025 through 6/12/2025 will be corrected on T+11M Settlement Statement. Trade Dates from 8/1/2024 through 8/7/2024 will be corrected on T+24M Settle | Base ETSRs shared with PACE and PACW | Resettling the impacted Trade Dates will fix the issue because issue is timing-related.​ | S​UG 5/3/26
30 | Dispute Issue: Dynamic ETSR Settlement. | For Dynamic ETSRs, duplicate records have been observed for the following Bill Determinants (BD). This issue is caused by timing/sequencing of incoming payloads and is related with the Settlements code deployment for DAME/EDAM.BA_5M_RSRC_EIM_XFER_TO_BAA_TAG_QTY andBA_5M_RSRC_EIM_XFER_FROM_BAA_TAG_QTY​​ | WEIM | 64770 | BA_5M_RSRC_EIM_XFER_TO_BAA_TAG_QTY,BA_5M_RSRC_EIM_XFER_FROM_BAA_TAG_QTY​​ |  | Pending Recal |  | Trade Dates 4/21/2026 - 4/29/2026 will be corrected on the T+70B Settlement Statement. | D​ynamic ETSR | Resettling the impacted Trade Dates will fix the issue because issue is timing-related. | S​UG 5/3/26
31 | Dispute Issue: Missing TSR Bill Determinant in Settlements | Settlements received ETSR and TSR input data, however, the associated records were subsequently terminated. This issue resulted in missing related BDs and led to incorrect ETSR and TSR settlement calculations. The impacted Trade Dates span from 5/1/2026 through 5/5/2026.​ | WEIM & EDAM | 8011, 8411, 8470, 8811, 64600, 64700 | TSR_15M_FMM_ENGY_FROM_QTY,TSR_5M_RTD_ENGY_FROM_QTY,TSR_5M_RTD_SCHD_FROM_QTY,TSR_HRLY_DA_ENGY_FROM_QTY |  | Pending Recal |  | Trade Dates 5/1/2026 - 5/5/2026 will be corrected on T+70B Settlement Statement. Issue was resolved starting Trade Date 5/6/2026. | E​TSR and TSR resources |  | S​UG 5/3/26
33 | DA Congestion PC, RT Congestion PC | Transfer Congestion was being paid out but not collected.​ |  | 6790, 64770, 6774, 67740, 4989 | N/A | 1681 | Pending Recal | 6/8/2026 | TD 5/1 – 5/20 T-9B initial Statement. It will be automatically corrected on T-70B Statement • TD 5/21 onward T-9B initial Statement will be correct. |  | Update Congestion Pre-Calcs and balancing for 4989 to correctly collect/ account for Transfer Congestion Amounts to then be allocated.​​ | ​SUG 6/10/26
34 | CC 8470 -Average Hourly FMM Price being used in Congestion calculation and incorrect sign | Incorrect Congestion Amounts calculated for FMM due to an averaging across the hour instead of by fifteen-minute granularity and reversed sign.​ |  | 8470 | BAA_5M_NODAL_FMM_ENGY_TRANSLOC_CONG@AMOUNT,BAA_5M_NODAL_RTD_ENGY_TRANSLOC_CONG@AMOUNT | 1681 | Pending Recal | 6/8/2026 | TD 5/1 – 5/20 T-9B initial Statement. It will be automatically corrected on T-70B Statement • TD 5/21 onward T-9B initial Statement will be correct. |  | Remove -1 multiplier from RTD and FMM Congestion Amount calculations and replace FMM hourly average price with FMM fifteen-minute price in congestion amount calculations​ | ​SUG 6/10/26
35 | CC 8080 - RSE potential for negative price of average LAP price needs a floor of $0. | Incorrect Congestion Amounts calculated for FMM due to an averaging across the hour instead of by fifteen-minute granularity and reversed sign. | EDAM & ISO BAA | 8080 | BAA_HRLY_EDAM_RSE_ON_PK_UP_CRED@AMOUNT | 1674 | Pending Recal | 5/22/2026 | 5/1/2026-5/11/2026 (T9B), will be automatically fixed in T70B; T9B for TD on or after 5/12/2026 is good |  | A Max function was added to the calculation of the Average LAP LMP to ensure that the minimum possible price would be $0 and not negative​​ | S​UG 6/3/26
36 | CC 6473 – Two Charge Types are missing in BD files | Reportability was set to “common” for two charge types, causing them not to appear in customer BD files.​​ Inability to shadow settlements all the way through 6473 due to the two charge types not present in the settlement files. No impact on Settlement amount.​​ |  | 6473 | BA_VIRT_DMND_FR_FM_STLMT@AMOUNT,BA_VIRT_SUP_FR_FM_STLMT@AMOUNT | 1674 | Pending Recal | 5/22/2026 | No financial impact to any TDs. • Reportability impact: 5/1/2026-5/11/2026 (T9B), will be automatically fixed in T70B; T9B for TD on or after 5/12/2026 is good. |  | The reportability was corrected to populate the charge types in the customer BD files.​ ​ | S​UG 6/3/26
37 | Wheel_Export_PC | Attributes were misaligned in formulation of BA_HRLY_RSRC_EXISTING_WHL_EXP@QUANTITY​ Output values of BA_HRLY_RSRC_EXISTING_WHL_EXP@QUANTITY were duplicated or triplicated. CC 382 and CC 384 amount will be impacted by this issue​. | ISO BAA | 382, 384 | BA_HRLY_RSRC_EXISTING_WHL_EXP@QUANTITY​ | 1674 | Pending Recal | 5/22/2026 | 4/20/2026-5/11/2026 (T9B), will be automatically fixed in T70B; T9B for TD on or after 5/12/2026 is good. • 1/29/2026-2/23/2026 (T70B), will be automatically fixed in T11M. T70B for TD on or after 2/24/2026 is good. |  | Formulation of SPTO_SUB_WHL_EXP@QUANTITY was modified to include a summation of (N, z’) attributes​ | S​UG 6/3/26
38 | RT_Price_PC - Logical Interface meters creating incorrect UFE Settlement for MSS | Logical Interfaces for MSS were being incorrectly included in the UFE pricing calculations. Incorrect pricing for UFE for MSS. Impacted CC 6474, only impact CISO BAA (MSS). ​​ ​ | ISO BAA | 6474 | UDC_HRLY_LAP_LOAD@QUANTITY | 1674 | Pending Recal | 5/22/2026 | 5/1/2026-5/11/2026 (T9B), will be automatically fixed in T70B; T9B for TD on or after 5/12/2026 is good. |  | Filtering the Logical Interfaces to exclude them from the pricing calculations will ensure correct pricing calculations​ | S​UG 6/3/26
39 | CC 64600 - HASP Reversal incorrect calculation for EDAM | HASP Reversal for EDAM was calculating an incorrect value due to a frequency conversion issue​. Incorrect HASP Settlement would occur due to the incorrect value calculation. This impact non-CISO EDAM entities only.​​ | EDAM | 64600 | BA_5M_RSRC_IMPRT_HASP_REV@AMOUNT,BA_5M_RSRC_EXPRT_HASP_REV@AMOUNT | 1674 | Pending Recal | 5/22/2026 | 5/1/2026-5/11/2026 (T9B), will be automatically fixed in T70B; T9B for TD on or after 5/12/2026 is good. |  | The formulas have been updated to correctly calculate HASP Reversal.​​ | S​UG 6/3/26
40 | CC 4989 - Incorrect rounding amount values in CC 4989 due to double counting of TSR congestion revenues. | Incorrect rounding amount values in CC 4989 due to double counting of TSR congestion revenues.​ |  | 4989 | N/A | 1674 | Pending Recal | 5/22/2026 | 5/1/2026-5/11/2026 (T9B), will be automatically fixed in T70B; T9B for TD on or after 5/12/2026 is good. |  | Remove the incorrect portion that goes to rounding CC 4989​. | ​SUG 6/3/26
41 | CC384 and CC 374 - Invoicing Net Amount Issue | Incorrect invoice for CC 384 due to changed attribute set of current amount with SPTO implementation. The current amount from previous run (January 2026 initial) is missing when the January 2026 T+70B was calculating the net amount for invoicing purposes.​​ | ISO BAA | 384, 374 | PTO_MTH_HVAC_REV_STL@NET_AMOUNT | 1680 | Open | 6/3/2026 | Feb to April 2026 T+70B Settlement Statements. Oct 2025-Jan 2026 T+11M Settlement Statements. No financial impact to any monthly final invoice.​ |  | Create an ad hoc PTB net amount adjustment to be able to reinstate the missing previous current amount value, to properly compute net amount and the invoice amount. This is expected to be used for Feb to April 2026 T+70B recalcs, and Oct 2025-Jan 2026 T+11M recalculations. This avoids the need for any supplemental invoice on the subject CCs. | ​SUG 6/3/26
42 | FRP_PC and CC 7088 - FRP Neutrality issue involving GWA and duplicate cost allocation | There is duplicate cost allocation under the GWA BAA, a generation only BAA, when there is conflicting SC_ID (the EIM entity SC and any participating SC) which metered load is zero for certain intervals. Impact: Small amount of duplicated allocation under CC 7076, 7077, and 7087 was observed. Monthly FRP uncertainty cost allocation CCs 7078 and 7088 are expected to also have the issue until resolved​​​​ |  | 7076, 7077, 7087, 7078, 7088 | BA_5M_BAA_SPEC_FR_FM_ALLOC@AMOUNT,BA_5M_BAA_SPEC_FR_MD_ALLOC_UNCERT@AMOUNT | 1680 | Pending Recal | 6/3/2026 | 5/6/2026-5/21/2026 (T9B), will be automatically fixed in T70B; T9B for TD on or after 5/22/2026 should be good. |  | Remove attribute BA_ID when checking for any generation only BAA. This is true only for second level allocation of unallocatable cost of forecasted movement to metered load or to the resource category buckets for uncertainty cost allocation. Updated FRP_PC and CC 7088​. ​ | ​SUG 6/3/26
43 | RT_NET_AMT_PC | FRP revenues (both forecasted movement and uncertainty award) included for RT BCR, which is incorrect.​​ Impact: Incorrect inclusion of FRP revenues for RT BCR. Impacted CC 6620 and 66200.​ |  | 6620, 66200 | BA_HRLY_BAA_RSRC_TOT_BCR_NON_ELIG_FLAG@QUANTITY | 1680 | Pending Recal | 6/3/2026 | 5/1/2026-5/21/2026 (T9B), will be automatically fixed in T70B; T9B for TD on or after 5/22/2026 should be good. |  | Fix FRP in eligibility flag to remove FRP revenues from RT BCR.​​​​​​ | ​SUG 6/3/26
44 | RT_Energy_PC - Duplicate BD, HASP Reversal | A driver issue was causing a duplication of records and settlements. Impact: Incorrect Settlement of HASP due to duplication. Impacted CC 6460 and CC 64600. | EDAM & ISO BAA | 6460, 64600 | BA_HRLY_RSRC_RC_DEV_CAP_TOT@QUANTITY,BA_HRLY_RSRC_HASP_EXP_REV_MW@QUANTITY,BA_HRLY_RSRC_HASP_IMP_REV_MW@QUANTITY | 1680 | Pending Recal | 6/3/2026 | 5/1/2026-5/21/2026 (T9B), will be automatically fixed in T70B; T9B for TD on or after 5/22/2026 should be good. |  | Corrected the equations to bring the inputs into alignment and included a HASP Reversal Flag into the equations.​ Note: Still some issues with HASP reversal payloads for PAC, sleaving this open to avoid confusion​​ | ​SUG 6/3/26
45 | RT_Energy_PC - Regulation Energy Calculation - Attribute Mismatch | Driver attributes were not in alignment, causing incorrect Regulation Energy Calculations. Impact: Incorrect Regulation Energy Quantity for EIM resources. Impacted CC 64700. | WEIM & EDAM | 64700 | BA_5M_RSRC_REG_ENGY@QUANTITY | 1680 | Pending Recal | 6/3/2026 | 5/1/2026-5/21/2026 (T9B), will be automatically fixed in T70B; T9B for TD on or after 5/22/2026 should be good. |  | Update the calculations to align the drivers to correct the attribute mismatch.​ ​​​​fixed in stage after 6/1 | ​SUG 6/3/26
46 | RT_Energy_PC - Operational Adjustment (OA) Quantity Calculations for EDAM Intertie Resources | Day Ahead Schedules were not considered for OA Quantity Calculations on EDAM Intertie Resources. Impact: Incorrect Incremental Settlements for FMM IIE. Impacted CC 64700.​ | EDAM | 64700 | BA_5M_EIM_RSRC_OP_ADJ_ENGY@QUANTITY | 1680 | Pending Recal | 6/3/2026 | 5/1/2026-5/21/2026 (T9B), will be automatically fixed in T70B; T9B for TD on or after 5/22/2026 should be good. |  | Update to include Day Ahead Schedules for EDAM Intertie Resources for correct incremental settlements for FMM IIE.​. | ​SUG 6/3/26
47 | BA_DAY_RTD_BAA_GHG_REG_AREA_FLAG | This Bill Determinant had Logical Interties included in the mapping, which was assigning these resources unintentionally. Impact: Incorrectly including Logical Interties in GHG Offsets. CC 495 is impacted.​ | EDAM & ISO BAA | 495 | BA_DAY_RTD_BAA_GHG_REG_AREA_FLAG | 1674 | Pending Recal | 5/22/2026 | 5/1/2026-5/11/2026 (T9B), will be automatically fixed in T70B; T9B for TD on or after 5/12/2026 is good. |  | Exclude the Logical Interties from appearing in this Bill Determinant to prevent these resources being associated to Real Time GHG Offset Settlement.​ | ​SUG 6/3/26
48 | Dispute Issue: Incorrect DA Virtual Award Quantities. BA_HRLY_DA_VIR_AWARD_NODAL_QTY | Virtual Awards Movement was calculated and sent from upstream to map to this BD for TDs prior to 5/1/2026. Mapping of BA_HRLY_DA_VIR_AWARD_NODAL_QTY incorrectly incorporated the virtual awards movement amount sent from upstream. Impacted CC 6013, 6073, 6985, 4560; indirectly CCs 6774, 67740, 6636, 6477 & 6478.​​ | ISO BAA | Directly impacted: 6013, 6073, 6985, 4560. Indirectly impacted: 6774, 67740, 6636, 6477 and 6478. | BA_HRLY_DA_VIR_AWARD_NODAL_QTY |  | Pending Recal |  | Trade Dates 2/7/2026-3/6/2026 will be corrected fixed on the T+11M Settlement Statement Any T+70B TD on or after 3/7/2026 has no issues. Trade Dates 4/25/2026-4/30/2026 will be corrected on the T+70B Settlement Statement. Any T+9B TD on or after 5/1/2 |  | Stop the virtual awards movement calculation for TDs prior to 5/1/2026​. | ​SUG 6/3/26
50 | Dispute Issue: IRUC/RCUC Capacity Calculation issues under the following conditions – When the resource is offline in IFM. | When the resource is offline in IFM (i.e., no Energy Awards) but still has IR (Imbalance Reserve) and RC (Residual commitment), the current logic does not calculate RCUC correctly. This issue resulted in incorrect RCU Settlements. The issue has been reviewed with Policy, and based on their guidance, the calculation logic will be updated for both IRUC and RCUC. No impact on IRD and RCD capacity calculations. ​​ | EDAM & ISO BAA | 8071, 8800 | BA_15M_RSRC_RCU_ALLOC_CAP_RANGE_QTY,BA_15M_RSRC_RCU_RA_OVERLAP_CAP_QTY,BA_HRLY_RSRC_RCU_AWARD_QTY,BA_HRLY_RSRC_RCD_AWARD_QTY |  | Closed |  | Trade Dates 5/1/2026 - 6/30/2026 | Resources offline in IFM with IR and RC Awards. ​ ​ | Fix was implemented on for TD 7/1/2026.​ TD 5​/1/2026 - 6/30/2026 will be corrected on the T+70B settlement cycle. ​ | ​SUG 6/3/26
51 | Dispute Issue: Incorrect IRU Tier 1 Allocation Quantities for Import Resources. | For Import and Export resources, operational PMIN and PMAX values are not defined. As a result, the Market Quality System (MQS) does not calculate the FMM Max Ex Cap quantity for import resources. Settlements currently does not incorporate pre-hour transmission schedule tags when deriving the IRU Tier 1 allocation quantity. This gap has resulted in inaccurate IRU Tier 1 allocation settlement calculations. We use the same pre-hour transmission schedule tags for IRD Tier 1 allocation for Export resources as well. The export side calculations have been implemented correctly. | EDAM & ISO BAA | 8076 | BA_15M_RSRC_FMM_MAX_EX_CAP_QTY | 1687 | Pending Recal | 7/9/2026 | Trade Dates Starting 5/1/2026 | Import resource​​ | The fix will be included in next Settlements release (Not included in June 3rd release). Once the fix is available, we will make corrections retrospectively from Trade Date 5/1/2026.​ Going in 7/8 release. For TD 6/28 init onwards​ | ​SUG 6/3/26
52 | Dispute Issue: Missing Data in Expected Energy Allocation report in CMRI. | An issue was identified with missing data in the Expected Energy Allocation (EEA) Details report within CMRI. Although the data was present in the underlying database, it was not being published to the report as expected. IT implemented an urgent patch to address the publishing issue, and the missing data has since been successfully populated in the EEA Details report. There were no discrepancies observed in the Expected Energy (EE) report within CMRI or in Settlements calculations. The issue was observed only for Trade Date 5/3/2026. ​ | ISO BAA | None | N/A |  | Closed |  | 5/3/2026 | ​Multiple Resources | Patch to address the publishing issue, and the missing data has since been successfully populated in the EEA Details report. | ​SUG 6/3/26
53 | Dispute Issue: Incorrect CRR information in CMRI impacting Settlement Validation. | ​An issue was identified involving incorrect Congestion Revenue Rights (CRR) information in CMRI. This discrepancy impacted SC’s ability to accurately validate CRR hourly settlement results. This issue has since been resolved, and the corrected data has been successfully updated in CMRI. Market participants may now access and download the revised reports for the impacted trade dates. | ISO BAA | 6700 | BA_DAY_CRR_NOTIONAL_AMT, BA_DAY_CRR_OFFSET_AMT |  | Closed |  | 5/1/2026 - 5/13/2026 | C​RR Holders | CMRI has been updated with correct data.​ | ​SUG 6/3/26
58 | Incorrect Virtual Award Quantity | The CMRI reflected the correct Virtual Award Quantity; however, this quantity was inaccurately represented in Settlements due to an incorrect mapping. ​ ​ |  | 6013 and the respective allocation charge codes. | BA_HRLY_DA_VIR_AWARD_NODAL_QTY | N/A | Pending Recal | 5/20/2026 | 4/25/2026 through 4/30/2026 (T+9B) |  | The mapping issue has now been identified and resolved. Corresponding corrections will be incorporated and reflected in the T+70B Settlement Statement​ ​ | S​UG 5/20/26
59 | Missing APN_TYPE (Attr14) | Incorrect mapping issue in Settlements created incorrect calculations for a few of the charge codes. |  | 495, 6011, 6477, 6774, 6788, 8011, 8404, 8704, 64770 and 67740 and the respective allocation charge codes. | Too many, just check missing APNODE_TYPE, which almost always come in pair with APN_ID |  | Pending Recal |  | 5/1/2026 through 5/3/2026 |  | The mapping issue has now been identified and resolved. Corrections will be incorporated and reflected in the T+70B Settlement Statement.​​ | S​UG 5/20/26​
61 | Missing FMM Awards for TD 5/8/2026, HE06, Interval 1 | We have identified missing FMM awards for HE06, Interval 1. This issue is related to market disruption.​ |  | 6460, 64600, 6470, 64700 and the respective allocation charge codes. | BA_15M_RSRC_FMM_CLEARED_ENGY_QTY |  | Pending Recal |  | 5/8/2026 |  | Corrections will be applied and reflected in the T+70B Settlement Statement​ Timing issue | S​UG 5/20/26
62 | Missing FMM Awards for TD 5/9/2026, HE24 | We have identified missing FMM awards for HE24. This issue is related to market disruption.​ |  | 6460, 64600, 6470, 64700 and the respective allocation charge codes. | BA_15M_RSRC_FMM_CLEARED_ENGY_QTY |  | Pending Recal |  | 5/9/2026 |  | Corrections will be applied and reflected in the T+70B Settlement Statement​. | S​UG 5/20/26
63 | No data in EDAM Balanced Contract Resources table in CMRI | This report is under External Entities > Extended Day-Ahead Market > EDAM Balanced Contract Resources​.​​​ | EDAM | None | BA_HRLY_RSRC_DA_BALANCE_CONTRACT_SCHD_QTY |  | Open |  | Starting from 5/1/2026 |  | CAISO will populate the relevant data soon. Based on our observations, no impact on Settlements Charge Code​​​s. | S​UG 5/20/26 ​7/16 - Mark R - this appears to be an education issue; may need to update the Settlements BPM
64 | Missing settlement for CC 4566 and 4567 for TD 4/20-4/23 published initial | GMC for system operations under the split CC 4566 and 4567 is zero. The input data for BA_DAY_EDAM_ENTITY_FLAG for CISO BAA was replaced incorrectly with effective date TD 5/1/2026​​. Additional background: A documentation only change, an implementation note under CC 4567 for below formula, shall be provided in the BPM update to CC 4567 (Emergency PRR).​​ |  | 4566, 4567 | BA_DAY_EDAM_ENTITY_FLAG |  | Pending Recal |  | 4/20/2026 - 4/23/2026 |  | This will be resolved in the next run cycle at T+70B​. | ​SUG 5/6/26
65 | No contracts balancing for TD 4/20-4/23/2026 initial | For these TDs, there will be no congestion hedge; no valid and balanced contract quantity exemptions to demand resource’s metered/measured demand allocations such as in CC 6790, 6774, 6477, 6636, 6678, Wheel export, and HVAC. Also, resources with TOR contract types will be subject to CC 4560 and 4566/4567 instead of 4563.​​​​ |  | CC 6790, 6774, 6477, 6636, 6678 Resources with TOR contract types will be subject to CC 4560 and 4566/4567 instead of 4563 | BA_HRLY_RSRC_DA_BALANCE_CONTRACT_SCHD_QTY,BA_5M_RSRC_FINAL_BALANCE_CONTRACT_SCHD_QTY |  | Pending Recal |  | 4/20/2026 - 4/23/2026 |  | This will be resolved in the next run cycle at T+70B.​ | ​SUG 5/6/26
67 | EDAM High: EIM Schedules by Priority Type | 6/15 Andrea: I still do not see any TSR Type 1 resources in the EIM Schedules by Priority Type CMRI report. I used trade date 6/9/2026 in stage for my test. I can see in SIBR we have a number of Type 1 Resources that do not show up in this report for this trade date in Stage. 6/16 Trang: have a fix for TSR in RT report that needs to be applied to our internal environment and validated there, and then will be promoted to Stage. ​ | PGE |  | TSR_5M_RTD_SCHD_FROM_QTY, TSR_5M_RTD_SCHD_TO_QTY |  | Open |  | 6/9 |  | CMRI report issue of market data | Patch applied to production on 07/06/2026. The TSRs are now showing up in this report. ​
68 | EDAM Medium: CC8076 missing intervals BA15MResFMMMaxExCap | 6/11 Andrea: PGE is waiting for adequate Stage settlement statement to validate this logic. Per our meeting with Uma Manoj Bryan and YesEnergy staff on 6/4/2026. Market Simulation Statements for PGE published in late April 2026 and May 2026 were incomplete. SIBR Bids rolled over from Day Ahead to Real Time were incomplete and MSQ data into settlements were incomplete.​ | EDAM | 8076 | BA_15M_RSRC_FMM_MAX_EX_CAP_QTY |  | Pending Customer Validation |  |  |  | Not a defect; need to educate PGE on design
69 | EDAM High: Missing results in EDAM Balanced Contract Resource CMRI report and Settlement of CC8704 DA Cong Offset | Question: In CMRI EDAM Balanced Contract Resources, What is the difference between “Market” Day Ahead, Post Day Ahead and Final? I looked in the BPM for Market Instruments and did not find a section for this report. Ref: CIDI 00299504 I think the behavior in CIDI ticket 00299504 is impacting Balanced Contract Resource CMRI and our settlement of CC8704 billing determinant BA_HRLY_RSRC_DA_BALANCE_CONTRACT_SCHD@QUANTITY and BA_HRLY_RSRC_OATT_CONTRACT_CONG_CREDIT@AMOUNT. ​ | PGE | 8704, 6011 | BA_HRLY_RSRC_DA_BALANCE_CONTRACT_SCHD@QUANTITY |  | Open |  |  |  | CMRI report issue (Settlement can handle)
70 | EDAM Med: ETC BA Hourly Load Balanced Contract Quantity missing | CC8077 and CC8076 use BASettlementIntervalResourceFinalBalancedContractCRNFilteredQuantity CC8077, CC8807, CC8087, CC8817 BAHourlyTotalLoadBalancedContractQuantity Calculated in PC ETC TOR CVR. This value will be negative for LOAD and ETIE resource types According to the Balanced Contract Report PGEM Load resource ELAP_PGE_PGEM_LOAD has 144 MWs of ETC Balanced Contract quantity on 6/11/2026 using CRN PGE_PGEE_ETC_BPAP and PGE_PGEE_ETC_PAC. PGEN has never received this determinant in their MRIS statement file. ​ | PGE | 8077, 8076 | BA_5M_RSRC_FINAL_BALANCE_CONTRACT_CRN_FILTERED@QUANTITY |  | Open |  |  |  |  | 7/6: We have validated RT CRN balancing for the requested Charge codes for TD 6/30/2026 STAGE, and the calculations are accurate. In addition, the initial had correct values for 6/23, the recalc made it worse, don't rely on the RECALK. In particular, the two bill_determinants are matching in nonzero values BA_5M_RSRC_FINAL_BALANCE_CONTRACT_CRN_FILTERED@QUANTITY BA_HRLY_TOT_LOAD_BALANCED_CONTRACT@QUANTITY on an hourly basis, if we filter only on LOAD resource types and do hourly aggregations.​
71 | EDAM Med: CC8011 Missing Transient TSR | The zero MW Energy Award was not making it to the data base, yet the resource had IR Award. Without this 0MW seen in the Award table the RTM Bid was not generated so no downstream bid for Post Market or Settlement. The IR should have been there for Settlement. ​ ​--- On Trade Date 6/11/2026 Recalc, SC PGEN, CC 8011 Day Ahead Imbalance Reserve Transfer Revenue Settlement I am having trouble validating the BABAATransferLocationNetIRQuantity and BAATransferLocationNetIRQuantity. It looks like the MWs related to PGEN_PGE_CISO_MALIN500_I_2_JD are in my CC8011 settlement result but the below 22 Transient Type 2 TSRs do not show up. All awards are at the same intertie of Malin500. PGEN-PGE_CISO_MALIN500_I-2-CISO-1 PGEN-PGE_CISO_MALIN500_I-2-CISO-10 PGEN-PGE_CISO_MALIN500_I-2-CISO-11 … ​ | PGE | 8011 | TSR_HRLY_DA_IR_FROM_QTY,TSR_HRLY_DA_IR_TO_QTY |  | Patch pending Validation |  |  |  | When TSR have DA awards , RT bids are not created​ | Vendor provided manual fix in testing. Target prod by 7/14 on SIBR patch 32
72 | Flex Ramp interval replacement price correction in WSU | For RTM 6/23, MVQA requested price corrections for interval replacement for both FRP and Energy + FRP. We noticed that FRP is no longer available as an interval replacement option in the PCA UI. Please advise on how to proceed. Would selecting the "ALL" commodity type be appropriate for the Energy + FRP correction? How should we handle the correction for the FRP commodity type, given that it is no longer available as an option? FRP interval replacement is an important requirement. The Price Correction tool previously supported this functionality. ​ |  |  | BA_15M_RSRC_FMM_FRU_BAA_PRC,BA_5M_RSRC_RTD_FRU_BAA_PRC |  | Patch pending Validation |  |  |  | Per Monique - The “All" button includes both energy and FRP. Please use that for the situation below.​If you are only processing FRP, we can do a back-end workaround to get these through while the defect gets assessed. | 7/7 - Manual workaround available
73 | Market - Clawback T+1 and T+8 runs for TD 6/18/2026 failed on LOAD_SF Processing Step | Clawback T+1 and T+8 runs failed on TD 6/18/2026 on LOAD_SF processing step. Please look into the root cause as this issue has resulted in no clean Clawback runs for this TD. This will possibly cause delays in invoicing or publishing of erroneous CRR settlement results.​ |  |  | BA_DAY_CRR_CLAWBACK_AMT |  | Open
74 | Dispute Issue: Missing Capacity Calculation for MSG Resources. | RTPD capacity for MSG (Multi-Stage Generator) resources was calculated correctly, but due to a processing issue, all corresponding RTPD capacity records were deleted. Missing records resulted in missing capacity inputs, which subsequently caused incorrect IR (Imbalance Reserve) and RC(Residual Commitment) settlement calculations.​​ | EDAM & ISO BAA | 8071, 8081, 8800, 8810 and the respective allocation charge codes. | BA_15M_RSRC_IRU_RA_OVERLAP_CAP_QTY,BA_15M_RSRC_RCU_RA_OVERLAP_CAP_QTY,BA_15M_RSRC_IRD_RA_OVERLAP_CAP_QTY,BA_15M_RSRC_RCD_RA_OVERLAP_CAP_QTY |  | Pending Recal |  | Trade Dates 5/1/2026 - 5/20/2026 will be corrected on the T+70B Settlement Statement. Issue was resolved starting Trade Date 5/21/2026 |  | Data is source system has been restored for impacted MSG resources and Trade Dates. ​ | SUG 6/3/26
75 | CC 384 Non-subscriber generation quantity not calculating for SPTO, and null BA_ID attribute created incorrectly for CC 384 and 374 | CC 384 Non-subscriber generation quantity not calculating for SPTO, and null BA_ID attribute incorrectly created for CC 384 and 374 settlement due to SPTO intertie allocation amount​ | ISO BAA | Wheel Export PC, 382, and 384. Indirect impact to 374 | SPTO_HRLY_NONSUB_GEN@QUANTITY,SPTO_HRLY_TAC_ALLOC@AMOUNT |  | Closed | 7/9/2026 | Retro to TD 10/1/2025 | SPTO​ | Update mapping for generation subscriber quantity to link resource to the SPTO, update existing and create new formulas to fix SPTO generation and intertie allocation amount.​ | SUG 7/8/26 Note: This issue was not a result of EDAM but will be fixed as part of the 7/8/2026 release.
76 | PROD: Duplicate records in SF and SF CSV files. |  |  |  | BA_DAY_CRR_NOTIONAL_AMT, BA_DAY_CRR_OFFSET_AMT |  | Closed | 7/9/2026 |  |  |  | 7/7 = YT - Fix in Production for TD 7/8 onward
77 | FMM ex-post capacities are not created for online resourcesM | MQS issue (affecting Colstrip resource) where FMM ex-post capacities are not created for online resources when IR/RC flags in MF are set to 'N'. Should be created regardless. This ultimately affects IRU Tier 1 allocation.CC 8076, 8086Discussing with Siemens 7/13. Communicated at noon on 7/13 to PGE/Andrea​ | EDAM | 8076, 8086 | BA_15M_RSRC_FMM_MAX_EX_CAP_QTY,BA_15M_RSRC_FMM_MIN_EX_CAP_QTY |  | Open
78 | Incorrect calculation of FMM LEL and FMM UEL | Defect 94059 (dup. of 94054)Incorrect calculation of FMM LEL and FMM UEL when the resource submits self-schedule with no economic bidsCC 8076, 8086​Discussing with Siemens7/13. Communicated at noon on 7/13 to Andrea |  |  | BA_15M_RSRC_FMM_MAX_EX_CAP_QTY,BA_15M_RSRC_FMM_MIN_EX_CAP_QTY |  | Open
79 | Load UIE not working | Defect 94074Fix in place last week for load UIE not working.​PGE aware, PAC filed dispute also. |  |  | BA_5M_RSRC_EIM_UIE_LAP_AMT@AMOUNT |  | Open
80 | TSRs with IRU award in DA without energy will not be suitable for validation in Stage TD | Missing input dates in SIBR. The zero MW Energy Award was not making it to the database, yet the resource had IR Award. Without this, 0MW seen in the Award table, the RTM Bid was not generated, so no downstream bid for Post Market or Settlement. The IR should have been there for Settlement.​ |  | 8011 | TSR_HRLY_DA_IR_FROM_QTY,TSR_HRLY_RT_IR_FROM_QTY |  | Closed |  | 6/25 | PGE | SIBR fix in Patch 33, expected for TD 7/7 onwards. Manually updated recently​ | Has been communicated to PGE
81 | Missing shift factor | Missing shift factors, missing calculating IRU/IRD in CRRS/Clawback and customers general concerns about the reduction in Congestion Rents in DA since EDAM. ​ |  |  | BA_DAY_CRR_NOTIONAL_AMT, BA_DAY_CRR_OFFSET_AMT,BA_DAY_CRR_CLAWBACK_AMT |  | Open | 6/19/2026
82 | CC 64750 - UIE Amounts were doubling for ELAPs. | This was traced to an attribute misalignment in the drivers that trigger the amount calculation that caused the amount to be calculated twice.​ | EDAM | 64750 | BA_5M_RSRC_EIM_UIE_LAP_AMT@AMOUNT, BA_5M_RSRC_EIM_UIEPLOADLAP@AMOUNT, BA_HRLY_EIM_FLTR_DMND@QUANTITY | 1689 | Pending Recal | 7/22/2026 | 6/30/2026 - 7/12/2026 |  | ​​​Attributes for the drivers of UIE amounts were updated to have all attributes aligned and a new version for BPM to clarify this.Attributes for the drivers of UIE amounts were updated to have all attributes aligned and a new version for BPM to clarify this. | SUG 7/22/26
83 | CC 495 - Driver issue | WEIM demand associated to GHG Area were not being allocated in the offset charge code correctly.​ | WEIM | 495 | RSRC_5M_BAA_DSPTCH_METER@QUANTITY | 1689 | Pending Recal | 7/22/2026 | 5/1/2026 - 7/12/2026 |  | Updated driver to correctly trigger 495 for GHG Area correctly, no BPM impact.​ | SUG 7/22/26 ​
84 | RTM_NET_AMT_PC - Missing intertie bid options flag incorrectly allows FRP revenue into BCR | ​ Intertie bid options flag for some intervals where FRP revenues are nonzero, are not always available nor provided to Settlements.​ | EDAM & ISO BAA | 6620, 66200 | BA_HRLY_BAA_RSRC_NON_BCR_TIE_BID_OPTION@FLAG | N/A | Pending Recal | 8/13/26 | 01/01/2025 onwards |  | ​Update RTM net amount pre-calculation. When interval value data for intertie bid options flag is not provided, then infer flag value based on a resource’s maximum flag value across the Trading Day. E.g., Input flag values 3, 4, 5, or 6 are ineligible, so if across Trading Day the maximum value obtained is at least 3, then resource is ineligible; else, resource is eligible.​ | SUG 8/12/26
85 | RTM_NET_AMT_PC - RTM net amount incorrectly excluding uncertainty award settlements for interties. | ​​Uncertainty award settlements for interties can be excluded incorrectly. This is not intended by Tariff 11.8.4.2.2 (d). | EDAM & ISO BAA | 6620, 66200 | BAA_BA_5M_RSRC_RT_NET@AMOUNT | N/A | Pending Recal | 8/13/26 | 01/01/2025 onwards |  | ​​Update RTM net amount pre-calculation, to move the uncertainty awards FRP revenues out of the exclusion for intertie FRP BCR. | SUG 8/12/26
86 | CC 64600, 64700 – Reporting Quantities | The BA_EIM_RSRC_5M_FMM_ETSR@QUANTITY and BA_EIM_RSRC_5M_RTD_ETSR@QUANTITY were calculating 0’s due to an attribute mismatch.​ | AVA, BPAT. We are investigating the root cause of the missing current price and current quantity. | CC 64600, 64700 | BA_EIM_RSRC_5M_FMM_ETSR@QUANTITY,BA_EIM_RSRC_5M_RTD_ETSR@QUANTITY |  | Pending Recal | 8/13/26 | Retro to TD 5/1/2026 |  | Intermediate charge types were created in CC 64600 and CC 64700 to align attributes and calculate these reporting quantities.​ | SUG 8/12/26​
87 | 6460 – Missing some FMM determinants | Only ITIE/ETIE were appearing in reporting quantity calculations when GEN/LOAD were also expected.​ | AVA, BPAT. We are investigating the root cause of the missing current price and current quantity. | CC 6460 | BA_5M_RSRC_FMM_IIE_STLMT_RPTG@QUANTITY | N/A | Pending Recal | 8/13/26 | Retro to TD 5/1/2026 |  | Updated the input for GEN/LOAD in the reporting quantity to calculate the reporting quantity for the full set of resources GEN/LOAD/ITIE/ETIE.​ | SUG 8/12/26​
88 | SPTO Charge Allocation Issue - Defect | SPTO received ActualDailyHighVoltageWheelingRevenuetoPTOSettlementAmount in Charge Code 384.​ | ISO BAA | CC 384 | PTO_MTH_INTERTIE_HV_WHL@AMOUNT,SPTO_DAY_WAC@AMOUNT,ISO_DAY_HVAC_DUE@AMOUNT | N/A | Pending Recal | 8/13/26 | Retro to TD 5/1/2026 |  | WIP, potentially update charges in PTO Allocation PC, CC 384 or CC 382 to nullify SPTO revenue values from current mechanism. Will be included with the mid-August release. Additional update to be provided in the next SUG.​ | SUG 8/12/26​
89 | Defect: CC 8080 Calculation Logic Update Needed for Tier 1 Off-Peak Flag | The BD, BAA_HRLY_EDAM_RSE_OFF_PK_UP_FAIL_SRCHG_TIER1@FLAG, in CC 8080 is outputting values of 1 when BAAEDAMRSEOffPeakHourlyUpwardDeficiencyQuantity Q'mdh is 0 during on-peak hours and BAAHourlyOffPeakIRUReqThresholdQuantity Q'mdh is 0 during on-peak hours. BAA_HRLY_EDAM_RSE_OFF_PK_UP_FAIL_SRCHG_TIER1@FLAG should equal 0 during on-peak hours. There is no financial impact as tier 1 RSE failures are de minimis and do not trigger charges in CC 8080.​ | CISO, PACE, PACW. None of these BAAs are financially impacted by this issue or resolution | CC 8080 | BAA_HRLY_EDAM_RSE_OFF_PK_UP_FAIL_SRCHG_TIER1@FLAG | N/A | Pending Recal | 8/13/26 | 5/1/26 |  | Update the calculation logic in CC 8080 of BAA_HRLY_EDAM_RSE_OFF_PK_UP_FAIL_SRCHG_TIER1@FLAG to output 0 during on-peak hours​ | SUG 8/12/26​
90 | CC495 - Redesign RT GHG Flag to align with DA GHG Flag | The way RT GHG Flag designed is not aligned with how the DA GHG Flag designed.​ | Scheduling Coordinators that have had GHG Area association | 495 | BA_5M_RTD_BAA_GHG_REG_AREA_FLG | N/A | Pending Recal | 8/13/26 | Retro to TD 5/1/2026 |  | Terminating the existing BD and redesign the Config for the RT GHG Flag - 'BA_5M_RTD_BAA_GHG_REG_AREA_FLG' and sourcing from real time resource awards.​ | SUG 8/12/26​
91 | Dispute- Virtual Award forecast movement | Monique to check if this was only a 1x occurrence TD 6/14/2026 Settlement impact CC 6473​ |  | 6473 |  |  | Open
92 | CRRS ifma flow for ITC constraints calculated incorrectly | ​For CRR1B calculation, there is an issue with ITC flow calculation for IFM due to TSR consideration and imbalance reserve award |  | 6700 |  |  | Open
93 | EDAM:RSE: All commitment cost should be treated as $0 | [5 empty] | Patch pending Validation | 7/24/26
94 | FA25: Ramping and consideration Base ETSRs and DA TSRs as hourly block in ISL and ITC constraints | [5 empty] | Patch pending Validation
95 | RCU pricing nomogram-related congestion component missing | Modify SIBR rules 31441, 31445, 31448 part of the 12.3.5.1 rule set.​ ​ |  |  |  |  | Patch pending Validation | 7/24/26
96 | CC 6011 – DA Marginal Energy and Loss Neutrality | Accounting of congestion at LAPs for the Day Ahead Energy MCC BAA breakdown uses a price that is incorrectly averaged across BAA instead of sum.​ | CISO and EDAM BAAs | Calculated in CC 6011, wrong output values into CC 8404 | LAP_HRLY_APN@PRICE,LAP_HRLY_DAM_APN@PRICE | 1696 | Closed | 8/13/26 | Retro to 5/1/26. TD 8/4 for T9B Initial, TD 5/10 for T70B re-calc forward | CISO and EDAM BAAs​ | Split the LAP MCC price into two, first average to the BAA level, then sum all BAAs to get the LAP price.​
97 | PCA - Incorrect prices for ETSR resources from price sync | The price sync process incorrectly synced the ETSR resource prices to the APnode price, instead of SP-TIE prices for BASE ETSR Resources. No workaround or fix in place.​ |  |  |  |  | Internal Review
98 | PCA - Exclude TSR resources from the Flex RAMP Forecast Movement and Uncertainty Movement. | TSR resources are getting movement calculation output applied to Settlement calculations​ |  |  |  |  | Internal Review
99 | DISPUTE : Incorrect SP-TIE association in PCA MF | ​​Base ETSRs may have incorrect prices on PCA correction records due to incorrect Intertie ID reference in PCA control data. Corrections are being applied by T70B with some corrections sooner. |  |  |  |  | Open
100 | Dispute: RA Overlap Capacity Not Calculating for SUNSET_2_UNITS and TD 5/1/2026 | In validating TD 5/1/2026 for SUNSET_2_UNITS to close a dispute, we discovered that the RA Overlap Capacity not calculating for certain hours. Please see the following details: TD 5/1/2026 Resource: SUNSET_2_UNITS DA: offline no awards for the whole day IR: no IRU/IRD awards RCD: no awards ​ |  |  |  |  | Open |  |  |  |  | 9/8 -This has to do with how PCA is digesting data from CIRA – Generic and Flex BFs. If both generic and flex MWs are the same, PCA placed both flags at 0, which precluded them from the overlapping RA calculation.​
101 | Dispute: RCD RA Overlap Quantity Calculation for RATSKE_2_NROSR1 TD 6/8/2026 | [5 empty] | Open
102 | FA25: RTCD not reporting priority breakdown | Priority breakdonw is not being reported for RTCD runs ​ |  |  |  |  | Open
103 | ETC_PC, 7076, 6011 – Three older bill determinant names has wrong termination date that overlaps with newer formulation | ​ With DAME/EDAM changes, three bill determinants particularly BA_5M_FR_FCAST_MVMT_ALLOC_STLMT@AMOUNT under CC 7076, BA_HRLY_ENGY_LOSS_CREDIT_ELIG_CONTRACT_DMND@QUANTITY under ETC_PC, and BA_HRLY_DA_ENGY@AMOUNT under CC 6011 were not terminated correctly​ | ETC_PC and 6011 is CISO BAA only; 7076 is all BAAs | CC 7076, 6011 and ETC_PC | BA_5M_FR_FCAST_MVMT_ALLOC_STLMT@AMOUNT, BA_HRLY_ENGY_LOSS_CREDIT_ELIG_CONTRACT_DMND@QUANTITY, BA_HRLY_DA_ENGY@AMOUNT |  | Pending Recal | 9/29/2026 | N/A | There was no financial impact from any of those errors. For 6011 and ETC_PC, the formulas were almost the same across effectivities; for CC 7076, despite different newer formulation. The newer was the ones picked correctly. No ICG/BPM change​ | ​Correct the termination dates for identified BDs​ | SUG 9/23
104 | RTM_NET_AMT_PC - Config - EIM non-participating resources needs to be BCR ineligible | EIM non-participating resources were getting BCR due to forecasted movement, however these are ineligible for BCR​ | EIM BAAs , not CISO BAA which didn’t have an issue to begin with | RTM_NET_AMT_PC | EIM_NPR_FLG |  | Pending Recal | 9/29/2026 | 1/1/2025 to cover T+21M run | Isolated to EIM non-participating resources only which had forecasted movement captured into CC 66200​ | Create a flag and make subject resources ineligible to receive BCR. A formula was updated in RTM_NET_AMT precalc​ | SUG 9/23​
107 | Bill Determinant Reportability Enhancements | We have updated the design of the following charge codes and intermediate charge types to enhance reportability of the settlement results for market participants. There is no financial impact resulting from these improvements. CC 64600 BAA_5M_RSRC_FMM_EIM_TRANS_TO@QUANTITY BAA_5M_RSRC_FMM_EIM_TRANS_FROM@QUANTITY CC 64700 BAA_5M_RSRC_RTD_TRANS_FROM@QUANTITY BAA_5M_RSRC_RTD_TRANS_TO@QUANTITY BA_BAA_RSRC_5M_RTD_ETSR_STLMT@AMOUNT - remove summation on attribute 3, Resource Type, in the formula to ensure visibility of the results for market participants. CC 6460 BA_5M_RSRC_FMM_IIE_PART1@QUANTITY - added as an input to the calculation of CAISO_6460_RPTG@FLAG in CC 6460. This ensures visibility of the results for market participants. ​ ​ | All BAAs | CC 64600, 64700, 6460 |  |  | Closed | 9/29/2026 | N/A | There is no financial impact resulting from these improvements​ | We have updated the design of the following charge codes and intermediate charge types to enhance reportability of the settlement results for market participants. There is no financial impact resulting from these improvements. CC 64600 BAA_5M_RSRC_FMM_EIM_TRANS_TO@QUANTITY BAA_5M_RSRC_FMM_EIM_TRANS_FROM@QUANTITY CC 64700 BAA_5M_RSRC_RTD_TRANS_FROM@QUANTITY BAA_5M_RSRC_RTD_TRANS_TO@QUANTITY BA_BAA_RSRC_5M_RTD_ETSR_STLMT@AMOUNT - remove summation on attribute 3, Resource Type, in the formula to ensure visibility of the results for market participants. CC 6460 BA_5M_RSRC_FMM_IIE_PART1@QUANTITY - added as an input to the calculation of CAISO_6460_RPTG@FLAG in CC 6460. This ensures visibility of the results for market participants. ​ | SUG 9/23​
108 | CC 8011, 8076, 8086, DA_CONG_PC - Neutrality issue sourced with IR Congestion | Congestion from Imbalance Reserve was being distributed, but not collected for Settlement​ | EDAM BAAs | CC 8011, 8076, 8086, 8086BD | BAADayAheadImbalanceReserveTransferLocationNetCongAmount Q'Qd'Q''kmdh DayAheadImbalanceReserveTransferSystemResourceMCCPrice rAA'Qpkmdh BAANodalDAIRTransferLocationCongAmount Q'AA'Qpkmdh ResourceDAIRTransferLocationQuantity rAA'Qpkmdh BAAHourlyIRDAllocati |  | Pending Recal | 9/29/2026 | 5/1/2026 to September release | It caused non-neutral settlement​ | Updates to the Congestion calculations to collect and distribute the congestion components of Imbalance Reserve in 8076, 8086 and 8704 respectively​ | SUG 9/23​
111 | CC 8080 - BAA_DAY_PERSIST_FAIL_VW@QUANTITY is not getting created for BAA that has tier2/3 for current TD under test | BAA_DAY_PERSIST_FAIL_VW@QUANTITY was not getting created for EDAM BAA that has tier 2 or 3 RSE upward failure for current TD under test​ | EDAM BAAs | CC 8080 | BAA_DAY_PERSIST_FAIL_VW@QUANTITY |  | Pending Recal | 9/29/2026 | 5/4/26, 6/17/26 | The persistent failure view quantity looks back at the previous rolling 30 days and counts the number of days across those 30 days in which the EDAM BAA had a tier 2 or 3 RSE upward failure during on-peak hours. This has a small impact on the RSE surcharge calculation in CC 8080. No ICG/BPM change​ | Add BAA_HRLY_EDAM_RSE_ON_PK_UP_FAIL_SRCHG_TIER_EVAL_FACTOR as an inclusionary business driver in the calculation of BAA_DAY_PERSIST_FAIL_VW@QUANTITY​ | SUG 9/23​
112 | Update HASP Reversal Calculations in CC64600 with CC6460 | The configuration of the HASP Reversal import and export amount calculations between CC 6460 and 64600 were not aligned. Unexpected results were caused by calculating the HASP reversal amount in 5 minute granularities for non-CISO vs in hourly time granularities for CISO​ | EDAM BAAs outside CISO | CC 64600 | BA_EIM_HRLY_RSRC_IMPRT_HASP_REV@AMOUNT, BA_EIM_HRLY_RSRC_EXPRT_HASP_REV@AMOUNT |  | Pending Recal | 9/29/2026 | 5/1/2026 onwards | This was causing an issue with the calculation of certain intervals that were not expected due to time granularity designations in the configuration/design of CC 64600​ | Update BPM and design for CC 64600 to align HASP reversal amount formulas with those in CC 6460​ | SUG 9/23​
115 | CC 6636 not using hourly net transfers-adjusted BCR uplift input from BCR sequential netting | Hourly net BAA transfers-adjusted cost amounts from BCR sequential netting pre-calculation was not used for allocation under CC 6636 IFM Bid Cost Recovery Tier 1 Allocation. Tariff section 33.11.3.5 requires the use of this IFM BCR uplift cost amounts. This removes the extra hourly aggregation in CC 6636.​​ | EDAM & ISO BAA | CC 6636 | BAA_HRLY_TOT_IFM_UPLIFT@AMOUNT, BAA_HRLY_NET_IFM_BID_COST_UPLIFT@AMOUNT |  | Closed | 9/29/2026 | 5/1/2026 onwards | CC 6636 and indirectly CC 6637 is incorrect because the uplift cost from EDAM BAA transfers, which shift BAA costs based on usage, are not properly accounted for​ | Update a formula in CC 6636 to use the hourly net transfers-adjusted uplift costs from BCR sequential netting​​ | SUG 9/23​