## EDAM Readiness
EDAM Readiness Criteria Worksheet |  |  | Link to EDAM Tariff | section-33-extended-day-ahead-market-as-of-jun-12-2024.pdf | This worksheet defines the specific criteria that must be met before the ISO and the EDAM entity agree they are ready for EDAM activation. This includes measurable elements that are documented in the tariff and specific thresholds.documented in the BPM. Tracking completion of the criteria will begin during Joint Integration Testing and will continue until 10 days prior to activation
# | Readiness Category | Evidence Owner | ISO Responsible Parties/support | Criteria | EDAM Measurable Elements (for tariff) | Threshold (for BPM) - current is from EIM | Notes | General Timing | Target Date | Current Est Completion Date | Status | Status Notes | Date Criteria Completed/Verified | Description of Evidence
1 | Execution of Necessary Agreements | Joint | John Anders/John Spomer/Regulatory contracts | Execution of Necessary Agreements | The prospective EDAM Entity and others as applicable have executed all necessary agreements. | The prospective EDAM Entity and others as applicable will execute all applicable agreements, as outlined in Section 33.2.5 of the EDAM BPM within the required timelines |  | Integration Testing |  |  | Not Started |  |  | EDAM Entity provide copies of all executed agreements. ISO provides evidence that the planned agreement tasks are all complete (Completed Agreements Checklist).
2 | Operations Training | EDAM Entity | Rashele Wiltzius | Mandatory training courses complete | Prospective EDAM Entity customers who will have responsibility for EDAM operations, market transactions and settlements, will complete CAISO training modules. EDAM Entity trainers will develop a training plan to educate its staff in preparation for EDAM implementation, and coordinate with trainers of third party entities within their areas to create a plan to educate their corresponding staff. | Prospective EDAM Entity staff, and third party entities within their area, will complete role-based training and close-of-training assessment in the appropriate timeframes as outlined in the EDAM Entity's Training Plan and the EDAM Course Catalog. | Customer Readiness—we believe that we will need a training curriculum for operations, markets and settlements for this initiative. | Parallel Operations |  |  | Not Started |  |  | EDAM Entity provides email evidence stating that all appropriate staff, including those identified in third party entities within their area, have received role-based training per the EDAM Entity's Training Plan and the EDAM Course Catalog, and the third party entities' EDAM/SC Training plan and EDAM/SC Course Catalog.
3 | Forecasting Capability | ISO | Amber Motley | Load forecast capability | · Definition of EDAM demand day ahead forecast boundaries based on the conforming and non-conforming load characteristics, as applicable · Identification of weather station(s) locations used in forecasting, if applicable · Entity has documented choice of Day Ahead Demand Forecast Provider and how demand forecasting will be completed · If entity provided day ahead demand forecast, then sign off on data flow of required demand forecast data from enity · Submittal of accuracy and evaluation of the CAISO or entity provided day ahead demand forecast of EDAM demand based on historical actual load data for the defined EIM demand forecast boundaries | All Plant Information (PI) tags and historical data for defined load area(s), and non-conforming load, if applicable, compared with DA load forecasts provided. EDAM entity provides documentation of forecast election. Forecasting entity must demonstrate delivery of Unit MW forecast by 6am for 1 day ahead through 7 days ahead. | updated by Rebecca | Market Simulation |  |  | Not Started |  |  | ISO Short term Forecasting team provides screenshots of EDAM BAA from Forecast Monitor showing accuracy measurements for DA.
4 | Forecasting Capability | ISO | Amber Motley | Variable Energy Resource (VER) forecast capability | · Identification of the source of day ahead VER forecasts. (If a participating wind or solar unit requires a CAISO forecast, then BPM and Tariff requirements apply.) · Idenfitication of all Hybrid Resources and applicable tariff and BPM requirements are met · Accuracy of the CAISO day ahead renewable forecast of EDAM VER resource | Real-time MW production PI tags for all Resources, and metrological measurements required for Hybrid Resources, compared with DA VER forecasts provided. EDAM entity provides documentation of forecast election. Forecasting entity must demonstrate delivery of Unit MW forecast by 6am for 1 day ahead through 7 days ahead. Forecasting entity must also provide DAM schedule. | updated by Rebecca | Market Simulation |  |  | Not Started |  |  | ISO short term forecasting sends email confirming that EDAM entity forecast provider demonstrated deliver of VER forecasts in Parallel Operations. They provided screenshots for wind and solar in Parallel Operations.
5 | Forecasting Capability | ISO | Amber Motley | Imbalance requirements | · Historical data on Day Ahead Demand and renewable forecast information to fill the needed historical data period to produce the imbalance requirements at the net load level · CAISO has established imbalance requirements for the prospective EDAM Entity Balancing Authority Area and the combined EDAM Area including the prospective EDAM Entity | The CAISO has received and stored all historical data from the prospective EIM Entity necessary and sufficient for the CAISO to perform the Imbalance Requirements. | updated by Rebecca | Market Simulation |  |  | Not Started |  |  | ISO Short term Forecasting team provides screenshots of EDAM Imbalance Requirements.
6 | Resource Sufficiency Evaluation | EDAM Entity | Juan Alvarez Lopez, Yu Wan | Resource Sufficiency Evaluation test | The prospective EDAM Entity Scheduling Coordinator demonstrates its ability to pass the resource sufficiency evalation test for the prospective EIM Entity’s Balancing Authority Area | Resource Sufficiency Evaluation Test passes 90% of the time (22 hours of the 2- hour day) or greater, with failed hourly intervals within 5% for each failed hour for one Trading day during Market Simulation, and for five non-consecutive days during Parallel Operations. |  | Market Simulation or Parallel Operations |  |  | Not Started |  |  | Screen shots of the RSE reports from CMRI report showing the 90% pass rate
7 | Transmission Availability | EDAM Entity | Jie Tong/Kelsey Ajax | The prospective EDAM Entity registers with the CAISO all the transfer path with other EDAM BAA that could be available for EDAM Transfers. | Validation of the completed EDAM entity TSR definition template. | The prospective EDAM entity submits the TSR definition template and it is approved by the CAISO team, and successfully registered in advance of Market Simulation. |  | Market Simulation |  |  | Not Started
8 | Operating Procedures | EDAM Entity | Rashele Wiltzius | Prospective EDAM Entity operating procedures | The prospective EDAM Entity operating procedures are defined, updated, tested, and trained on for the EDAM Entity Scheduling Coordinator, in coordination with third party entites within their area. | The prospective EDAM Entity and its Scheduling Coordinator's operating procedures are updated, tested, trained and implemented in coordination with third party entities within their area prior to parallel operations date. | Customer Readiness—for WEIM, we just verify that the customer has created their own procedures. We can do something similar for EDAM. | Parallel Operations |  |  | Not Started |  |  | EDAM Entity provides screen shots and an email confirming the documentation is complete.
9 | System Readiness & Integration | Joint | Rashele Wiltzius | Prospective EDAM Entity Identification and system certificates and access | Validation of SCID’s and Resource ID’s. All prospective EDAM Entity employees who require system access to perform EDAM-related job functions identified and have necessary certificates. | All prospective EDAM Employees performing job functions for EDAM market are identified. All CAISO issued certificates are requested within the appropriate timeframes. All identified employees provided the necessary EDAM system access certificates. | Customer Readiness – combined into one and listed Customer Readiness as the owner (same as Track 2) | Integration Testing |  |  | Not Started |  |  | EDAM Entity provides an email stating that all access is in place for Parallel Operations and a plan is in place to ensure all access is in place for production. ISO Client Rep provides an email confirming that access is in place and there is a plan for ensuring access for Production.
10 | Market Simulation | Joint | Sriram Balasubramian | Market Simulation and structured scenario execution | The prospective EDAM Entity operators execute and pass all structured scenarios provided by CAISO. | All significant issues resolved or have an interim solution that is functionally equivalent. | Yes, We need to ensure the structured scenarios are complete and represent validation of full scope needed for EDAM onboarding as well the interplay with corresponding WEIM market for the same entity. | Market Simulation |  |  | Not Started |  |  | ISO provides a completed Structured Scenario Reports (Detailed Input-Output for Structured Scenarios by week) and a Structured Scenario Status matrix. EDAM Entity sends a confirmation email identifying any approved incomplete cases/validations. ISO sends confirmation email.
11 | System Readiness & Integration | EDAM Entity | Jamil Daouk | System and Functional Testing | The prospective EDAM Entity will test the functional and system elements, including all interfaces between CAISO and the EDAM Entity, in accordance with functional and system testing documentation posted on the CAISO website | All tasks identified in the functional and system testing documentation are complete and will not have any issues deemed significant. Any exceptions will be explained or have an interim solution that is functionally equivalent. |  | Integration Testing |  |  | Not Started |  |  | EDAM Entity provides the EDAM Testing Timeline Summary indicating that the Functional Testing is complete. EDAM Entity may also include reports from their test system showing that all test cases were executed and passed, identifying any approved incomplete cases and interim solution. ISO Integration Lead sends confirmation email.
12 | Settlements | Joint | James Lynn / Uma Ramanathan | EDAM Scheduling coordinators (Entity or PRSC) direct settlement with CAISO. | The CAISO Settlement statements and invoices match the operational data published to stakeholders or fed into settlement system and the resulting calculations correspond to the formulas defined in ISO’s tariff and BPMs | Daily and /or Monthly settlement statement and Weekly invoice that correspond with appropriate Settlement statements. Settlements produced during parallel operations are verifiably accurate against available data. |  | Parallel Operations |  |  | Not Started
13 | Settlements | Joint | James Lynn / Uma Ramanathan | EDAM entities Settlement sub-allocations of Costs assigned to the EDAM entity. | Verification that settlement statements and invoices allocates charges and credits to its customers accurately reflecting system and market data. | The prospective Entity settlement statements and invoices that allocate charges and credits to its customers accurately reflect system and market data during parallel operations. |  | Parallel Operations |  |  | Not Started
14 | Historical Transmission Revenue Recovery | Joint | James Lynn / Uma Ramanathan | The EDAM Entity provides the CAISO with the information necessary to account for the EDAM recoverable revenue associated with the EDAM Transmission Service Providers in its Balancing Authority Area. If they are not going to provide, it should not prevent go-live. Note: If the entity does not provide us the information, we will use mock up information for parallel operations however it will not be updated to production. (EDAM access charge). | Verification that the EDAM Entity submitted EDAM recoverable revenue has been incorporated into the EDAM recoverable charge codes including EDAM recoverable rates and assessment to gross load. | Daily settlement statement and Weekly invoice that correspond with appropriate Settlement statements. Settlements produced during parallel operations are verifiably accurate against available data. |  | Market Simulation or Parallel Operations |  |  | Not Started |  |  | Calculate the EDAM Access charge based upon EDAM recoverable amount provided by entity.
15 | Parallel Operations | Joint | Sriram Balasubramian | Parallel Operations Technology Criteria | Ensures all transfers between neighboring BAs, EDAM and WEIM entities are configured accurately for market operations and settled correctly. | DA market Completion within timeline 90% of the time Validation of market results, DAM solution of EDAM participants Validation of WEIM output and solution of EDAM and existing EIM-only Entities |  | Parallel Operations |  |  | Not Started
16 | Parallel Operations | ISO | Guillermo Bautista Alderete / Heifeng | Parallel Operations market quality review | Market results are appropriate and prices are validated based on input data during Parallel Operations. | Parallel operations prices and MWs schedules/dispatches are validated by the CAISO market quality team - trying not to formally file with FERC - 10 days prior to activation it will be a joint review and agreement of readiness. No specific requirement for a market quality report. |  | Parallel Operations |  |  | Not Started |  |  | ISO Market Quality team provides analysis report on the Market Solution, prices, and quality of data.

## Graphs
EDAM Readiness Criteria ¦ Status as of: MM/DD/YYYY
Readiness Category: |  |  | Status | Count of Readiness Category
Status | Not Started | Grand Total | Not Started | 16 | \
(blank) | 16 | 16 | Grand Total | 16
Grand Total | 16 | 16

## Summary
Completion Criteria Summary
Last Updated:
EDAM readiness Criteria | Complete | On Track | Caution | Not Started
| #REF! | #REF! | #REF! | #REF!
# of Criteria | 0 | 0 | 0 | 16
| 0% | 0% | 0% | 100%
Total criteria | 16

## Valid Fields
Status
Not Started
On Track
Caution
Off Track
Complete
section-33-extended-day-ahead-market-as-of-jun-12-2024.pdf